## Read Me
PolymathTransit – User Stories, Backlog & Traceability
Version | 0.1
Date | 30/09/2026
Status | DRAFT – for stakeholder review
Author | Srimal
Companion document | PolymathTransit_Requirements_Specification_v0.1.docx
Sheet | Contents
Epics | Epic summary with story count, points and T-shirt size
User Stories | Full backlog with acceptance criteria (Given/When/Then), priority, points, complexity, status
Requirements | Catalogue of business, functional and non-functional requirements
Business Rules | Allocation rules the engine must apply
RTM | Traceability: objective → BR → FR → story → test case, with test & delivery status
Open Questions | Questions to resolve before design, with owner and status
Risks | Risk register
Priorities | MoSCoW – Must (Release 1 MVP), Should (Release 2), Could (later)
Story points | Indicative Fibonacci estimates (confidence Low, ±60%) – to be re-estimated by the delivery team

## Epics
Epic ID | Epic | Theme | Description | Business value | Stories | Points | T-shirt
EP-01 | Transport Request (Public Form) | T1 – Easy access for staff | A public, mobile-friendly form where staff request a van with minimal typing. | One channel for all requests; form completed in 2 minutes or less (BO-04). | 7 | 23 | L
EP-02 | Fixed & Recurring Trips | T2 – Efficient, automated scheduling | Set up regular trips once per term; occurrences are booked automatically, and school/public holidays are skipped. | Known commitments always covered; removes weekly re-booking (BO-01). | 5 | 19 | M
EP-03 | Automatic Allocation | T2 – Efficient, automated scheduling | Rules-based engine that proposes the best van (and driver) for each trip and explains why. | Most allocations approved without change; zero double bookings (BO-01, BO-02, BO-03). | 9 | 44 | XL
EP-04 | Coordinator Review & Scheduling | T2 – Efficient, automated scheduling | Dashboard, approvals, changes, calendar and run sheets for coordinators. | Coordinators stay in control with far less effort (BO-01, BO-05). | 8 | 30 | L
EP-05 | Notifications & Requester Self-Service | T1 – Easy access for staff | SMS/email updates and a secure no-login link to check or cancel a booking. | Requesters always know where they stand; cancellations free vans quickly (BO-05). | 5 | 17 | M
EP-06 | Fleet, Driver & Location Management | T3 – Safe, scalable and accountable operation | Maintain vans, drivers, locations, travel times, term dates and rules without IT help. | The system scales with the fleet; compliance dates are never missed (BO-02, BO-06). | 5 | 15 | M
EP-07 | Reporting & Insights | T3 – Safe, scalable and accountable operation | Utilisation, demand and unmet-request reports; exports. | Evidence-based fleet decisions (BO-03). | 3 | 10 | M
EP-08 | Security, Privacy & Audit | T3 – Safe, scalable and accountable operation | Secure staff login, privacy compliance and a complete change history. | Personal information protected; decisions traceable (BR-10, BR-11). | 3 | 9 | M
TOTAL

## User Stories
Story ID | Epic | Epic name | User story | Acceptance criteria | Priority | Points | Complexity | Traces to (FR) | Target release | Status | Notes
US-01 | EP-01 | Transport Request (Public Form) | As a teacher, I want to request a van from a simple web form on my phone without logging in, so that I can book transport in under two minutes, wherever I am. | AC-1: GIVEN I open the request form link or scan the QR code on my phone WHEN the page loads THEN I see a single page with plain-language questions and no login or sign-up prompt AC-2: GIVEN I leave 'Your name' or 'Phone number' empty WHEN I tap 'Send request' THEN the form is not sent and shows 'Please enter your name' / 'Please enter a phone number' next to the field AC-3: GIVEN I enter 021 123 4567 or (09) 123 4567 WHEN I tap 'Send request' THEN the number is accepted and stored as +64211234567 / +6491234567 AC-4: GIVEN I enter a trip date in the past, or a return time before the departure time WHEN I tap 'Send request' THEN a plain-language error explains what to fix and the form is not sent AC-5: GIVEN all mandatory fields are valid WHEN I tap 'Send request' THEN within 3 seconds I see 'Request received' with a reference (e.g. PT-2026-0142) and a summary of my trip | Must | 5 | Medium | FR-01, FR-02, FR-03, FR-04 | Release 1 (MVP) | Draft
US-02 | EP-01 | Transport Request (Public Form) | As a requester, I want to choose my pickup and destination from a list, with an 'Other address' option, so that I don't have to type addresses and the system knows the travel times. | AC-1: GIVEN the administrator has 3 active campuses and 4 active venues WHEN I open the pickup or destination list THEN I see only those 7 active locations, grouped as 'Our campuses' and 'Venues', plus 'Other address' AC-2: GIVEN I choose 'Other address' WHEN the option is selected THEN a mandatory 'Address' field appears AC-3: GIVEN I submit a request with an 'Other address' WHEN allocation runs THEN the request is set to 'Needs attention' with the reason 'Unlisted address – check travel time' | Must | 3 | Low | FR-02, FR-05 | Release 1 (MVP) | Draft
US-03 | EP-01 | Transport Request (Public Form) | As a requester, I want to say how many people are travelling and whether the van must wait with us, so that a van of the right size is allocated and it is freed up when not needed. | AC-1: GIVEN I am on the form WHEN I reach 'Does the van need to wait with your group?' THEN I can choose 'Yes, wait with us', 'No, drop us off and collect us later' or 'One way only' AC-2: GIVEN I choose 'Drop us off and collect us later' WHEN the option is selected THEN a mandatory 'Collection time' field appears, and 'Return time' is hidden AC-3: GIVEN the largest van has 12 passenger seats WHEN I enter 20 passengers THEN I see 'This group needs more than one van – we'll arrange this' and can still submit AC-4: GIVEN I enter 0 or more than 99 passengers WHEN I submit THEN I see 'Please enter a number between 1 and 99' | Must | 3 | Medium | FR-02, FR-06 | Release 1 (MVP) | Draft
US-04 | EP-01 | Transport Request (Public Form) | As a requester, I want to tell the coordinator about special requirements such as wheelchair access or sports gear, so that a suitable van is provided. | AC-1: GIVEN I tick 'Wheelchair access needed' WHEN allocation runs THEN only vans with the wheelchair-access feature are considered and the request is set to 'Needs attention' for a coordinator check AC-2: GIVEN I tick 'Large equipment' WHEN allocation runs THEN only vans with large-luggage capacity are considered AC-3: GIVEN I type in 'Anything else we should know?' WHEN a coordinator opens the request THEN the note is shown prominently on the request | Should | 2 | Low | FR-09 | Release 2 | Draft
US-05 | EP-01 | Transport Request (Public Form) | As a requester, I want to be warned if I'm booking at short notice or outside operating hours, so that I know my request might not be possible and can make a backup plan. | AC-1: GIVEN the minimum notice is 24 hours WHEN I choose a trip starting in 5 hours THEN I see 'Short notice – we'll try, but can't guarantee a van. For urgent help call <coordinator number>' and can still submit AC-2: GIVEN the request is submitted at short notice WHEN a coordinator views the dashboard THEN the request shows an 'Urgent' tag and sorts to the top AC-3: GIVEN operating hours are Mon–Fri 07:00–18:00 WHEN I choose Saturday 09:00 THEN I see an 'Outside normal hours' warning, and the request is flagged 'Out of hours' | Should | 2 | Low | FR-07 | Release 2 | Draft
US-06 | EP-01 | Transport Request (Public Form) | As a transport coordinator, I want to have the public form protected against spam and misuse, so that I only deal with genuine requests. | AC-1: GIVEN an automated script fills the hidden honeypot field or fails the invisible CAPTCHA WHEN it submits THEN the request is rejected silently and not shown to coordinators AC-2: GIVEN a phone number has already made 5 submissions in the past hour WHEN a 6th is submitted THEN it is blocked with 'Too many requests – please call the transport office' AC-3: GIVEN a phone number has never been used before WHEN the request is submitted THEN it is tagged 'New requester' and set to 'Needs attention' | Must | 3 | Medium | FR-08 | Release 1 (MVP) | Draft
US-07 | EP-01 | Transport Request (Public Form) | As a requester, I want to see roughly which times are free on my chosen date, so that I can choose a time that is likely to be available. | AC-1: GIVEN Van 1 and Van 2 are both booked 9:00–11:00 on 12/03/2027 WHEN I choose 12/03/2027 on the form THEN I see 9:00–11:00 marked 'Busy' and other school hours marked 'Likely free' AC-2: GIVEN availability is shown WHEN I look at busy periods THEN no details of other bookings (names, destinations) are visible | Could | 5 | Medium | FR-10 | Later | Draft
US-08 | EP-02 | Fixed & Recurring Trips | As a transport coordinator, I want to set up a recurring fixed trip (e.g. Swimming, every Tuesday 10:00–12:00, Terms 1–4), so that these trips are booked automatically without re-entering them. | AC-1: GIVEN I create the series 'Year 7 Swimming', weekly on Tuesday 10:00–12:00, Main Campus → Aquatic Centre, 11 passengers, Term 1 2027 WHEN I save THEN an occurrence is created for every Tuesday school day in Term 1 2027 and each is allocated AC-2: GIVEN I leave the name, day, times, pickup, destination or date range empty WHEN I save THEN the series is not saved and the missing fields are highlighted AC-3: GIVEN the series has a contact person and phone WHEN occurrences are confirmed THEN the contact receives one summary SMS for the term, not one per occurrence | Must | 5 | Medium | FR-11 | Release 1 (MVP) | Draft
US-09 | EP-02 | Fixed & Recurring Trips | As a transport coordinator, I want to have recurring trips skip school holidays and public holidays automatically, so that vans aren't reserved on days when there's no school. | AC-1: GIVEN a Tuesday falls in the school holidays WHEN the series is generated THEN no occurrence is created for that Tuesday AC-2: GIVEN a Monday is a NZ public holiday WHEN a Monday series is generated THEN no occurrence is created for that Monday AC-3: GIVEN the administrator adds a teacher-only day after the series exists WHEN the calendar is saved THEN the occurrence on that day is cancelled, its van is released, and the series contact is notified | Must | 3 | Medium | FR-12 | Release 1 (MVP) | Draft
US-10 | EP-02 | Fixed & Recurring Trips | As a transport coordinator, I want to change or cancel a single occurrence without affecting the rest of the series, so that one-off changes such as a cancelled swimming session are easy. | AC-1: GIVEN the 'Year 7 Swimming' series has 10 occurrences WHEN I cancel the 14/05 occurrence only THEN only that occurrence is cancelled, its van is released and the other 9 are unchanged AC-2: GIVEN I change the time from 10:00 to 11:00 and choose 'this and all following' WHEN I save THEN that occurrence and all later ones move to 11:00 and are re-allocated; earlier ones are unchanged | Must | 3 | Medium | FR-13 | Release 1 (MVP) | Draft
US-11 | EP-02 | Fixed & Recurring Trips | As a transport coordinator, I want to have fixed trips allocated before ad-hoc requests, so that known commitments are always covered. | AC-1: GIVEN an ad-hoc request is Proposed on Van 1 on Tuesday 10:00 WHEN I create a fixed series that needs Van 1 at that time and no other van fits THEN the fixed occurrence takes Van 1 and the ad-hoc request is re-allocated or moved to 'Needs attention' AC-2: GIVEN the ad-hoc request was already Confirmed WHEN the fixed series is created THEN the Confirmed booking is not moved; the clash is shown to me to resolve | Must | 3 | Medium | FR-14 | Release 1 (MVP) | Draft
US-12 | EP-02 | Fixed & Recurring Trips | As a transport coordinator, I want to import a term's fixed trips from a spreadsheet, so that I can set up a whole term quickly. | AC-1: GIVEN I upload a file based on the download template WHEN the file is processed THEN I see a preview showing valid rows and rows with errors (with reasons) before anything is saved AC-2: GIVEN I confirm the import WHEN it completes THEN valid series are created and allocated exactly as if I had entered them manually | Could | 5 | Medium | FR-15 | Later | Draft
US-13 | EP-03 | Automatic Allocation | As a transport coordinator, I want to have each new request automatically allocated to a suitable van, so that I only need to check and approve. | AC-1: GIVEN a valid request is submitted and a feasible van exists WHEN allocation runs THEN within 5 seconds the request is 'Proposed' with the van (and driver if enabled) shown AC-2: GIVEN a booking is cancelled WHEN allocation re-runs THEN unconfirmed bookings may be re-allocated, but no Confirmed booking is changed AC-3: GIVEN allocation runs WHEN it finishes THEN the decision is written to the audit log as 'System – automatic allocation' | Must | 8 | High | FR-16, FR-23 | Release 1 (MVP) | Draft
US-14 | EP-03 | Automatic Allocation | As a transport coordinator, I want to be sure the system never double-books a van, allowing travel and turnaround time between trips, so that trips don't run late or clash. | AC-1: GIVEN Van 1 returns to Main Campus at 11:30, the turnaround buffer is 15 min and North Campus is 20 min from Main Campus WHEN a request needs a van at North Campus at 11:50 THEN Van 1 is not proposed (earliest arrival 12:05) AC-2: GIVEN Van 1 is on a 'Drop off and collect later' trip, free between 10:30 and 13:30 at the Aquatic Centre end WHEN a request fits within that gap including travel and buffers THEN Van 1 can be proposed for it AC-3: GIVEN the same van is proposed for two overlapping trips WHEN any allocation or manual save is attempted THEN it is prevented, and the clash is described (van, times, other booking) | Must | 5 | High | FR-17 | Release 1 (MVP) | Draft
US-15 | EP-03 | Automatic Allocation | As a transport coordinator, I want to have the smallest suitable van chosen, preferring one already at or near the pickup, so that the fleet is used efficiently. | AC-1: GIVEN an 8-seat van and a 12-seat van are both free WHEN a request for 6 passengers is allocated THEN the 8-seat van is proposed AC-2: GIVEN two identical vans are free, one at the pickup campus and one 25 min away WHEN a request is allocated THEN the van at the pickup campus is proposed AC-3: GIVEN the administrator changes preference weights WHEN the next allocation runs THEN the new weights are used and the change is audit-logged | Must | 5 | High | FR-18 | Release 1 (MVP) | Draft
US-16 | EP-03 | Automatic Allocation | As a transport coordinator, I want to see in plain words why the system chose a van, so that I can trust or change its decision. | AC-1: GIVEN a request is Proposed WHEN I open it THEN I see a reason such as 'Van 2: 12 seats fits 9 passengers; already at Main Campus. Van 1 busy 9:00–11:30 (Swimming).' AC-2: GIVEN a request is 'Needs attention' WHEN I open it THEN I see which rule blocked each van, e.g. 'Van 1 – WOF expired 02/03' | Should | 3 | Medium | FR-19 | Release 2 | Draft
US-17 | EP-03 | Automatic Allocation | As a transport coordinator, I want to have requests that can't be allocated flagged with suggested alternatives, so that I can resolve them quickly. | AC-1: GIVEN no van is free at the requested time WHEN allocation runs THEN status is 'Needs attention' and I see up to 3 options, e.g. 'Van 1 free if departing 10:40' or 'Swap with unconfirmed PT-2026-0139' AC-2: GIVEN I pick a suggested option WHEN I confirm it THEN the booking is updated and the requester is notified of the change AC-3: GIVEN no alternative exists WHEN I open the request THEN I see 'No alternatives in ±60 min' and the conflicting bookings | Must | 5 | High | FR-20 | Release 1 (MVP) | Draft
US-18 | EP-03 | Automatic Allocation | As a transport coordinator, I want to be told when two requests could share a van, so that we reduce the number of trips. | AC-1: GIVEN two requests go Main Campus → Sports Centre departing 9:00 and 9:10 with 5 and 4 passengers, and a 12-seat van is available WHEN the second request is allocated THEN both show 'Could share with PT-xxxx' with a 'Combine' button AC-2: GIVEN I click 'Combine' WHEN I confirm THEN both are allocated to one van with the earlier departure time, and both requesters are notified of any time change AC-3: GIVEN the combined passengers exceed the van seats WHEN allocation runs THEN no suggestion is made | Should | 5 | Medium | FR-21 | Release 2 | Draft
US-19 | EP-03 | Automatic Allocation | As a transport coordinator, I want to have large groups split across several vans automatically, so that I don't have to create separate bookings. | AC-1: GIVEN vans have 12 and 8 passenger seats WHEN a request for 18 passengers is allocated THEN both vans are proposed on one booking, departing together AC-2: GIVEN not enough vans are free for the whole group WHEN allocation runs THEN the request goes to 'Needs attention' with the reason 'Group needs 2 vans; only 1 free' | Should | 5 | Medium | FR-22 | Release 2 | Draft
US-20 | EP-03 | Automatic Allocation | As a transport coordinator, I want to be sure a van under maintenance or with an expired WOF/registration is never allocated, so that we stay safe and legal. | AC-1: GIVEN Van 1's WOF expires on 02/03/2027 WHEN a request for 03/03/2027 is allocated THEN Van 1 is excluded with the reason 'WOF expired' AC-2: GIVEN Van 2 has a maintenance block 10/03 08:00–12:00 WHEN a request overlaps that block THEN Van 2 is excluded AC-3: GIVEN a coordinator tries to assign a non-compliant van manually WHEN they save THEN the save is blocked with the reason | Must | 3 | Medium | FR-17, FR-40 | Release 1 (MVP) | Draft
US-21 | EP-03 | Automatic Allocation | As a transport coordinator, I want to have an available, approved driver allocated along with the van, so that every trip has an eligible driver (if the college uses assigned drivers – see Q-01). | AC-1: GIVEN driver allocation is enabled and Driver A is on leave on 05/03 WHEN a trip on 05/03 is allocated THEN Driver A is not proposed AC-2: GIVEN Driver B's licence expired WHEN allocation runs THEN Driver B is never proposed, and admins were reminded 14 days before expiry AC-3: GIVEN driver allocation is disabled in settings WHEN allocation runs THEN only a van is allocated, and the requester is shown as the responsible driver | Should | 5 | High | FR-24 | Release 2 | Draft
US-22 | EP-04 | Coordinator Review & Scheduling | As a transport coordinator, I want to see a dashboard of requests awaiting my action, sorted by trip date and urgency, so that I handle the most pressing ones first. | AC-1: GIVEN there are 2 Needs-attention, 5 Proposed and 1 Urgent request WHEN I sign in THEN I see tiles 'Needs attention (2)', 'Awaiting approval (5)', 'Urgent (1)', 'Today's trips (n)', with Urgent items first AC-2: GIVEN I click a tile WHEN the list opens THEN it shows trip date/time, requester, route, passengers, proposed van and status, and can be filtered AC-3: GIVEN the other coordinator approves a request WHEN I am viewing the dashboard THEN the counts refresh within 30 seconds without reloading, so we don't act on the same item twice | Must | 5 | Medium | FR-25 | Release 1 (MVP) | Draft
US-23 | EP-04 | Coordinator Review & Scheduling | As a transport coordinator, I want to approve a proposed allocation in one click, or several at once, so that confirming is quick. | AC-1: GIVEN a request is Proposed WHEN I click 'Approve' THEN it becomes Confirmed and the requester receives the confirmation SMS within 1 minute AC-2: GIVEN I tick 6 Proposed requests WHEN I click 'Approve selected' THEN all 6 are Confirmed and 6 SMS are sent AC-3: GIVEN another coordinator already changed the request WHEN I click 'Approve' THEN I'm told it changed and shown the latest version before approving | Must | 3 | Low | FR-26 | Release 1 (MVP) | Draft
US-24 | EP-04 | Coordinator Review & Scheduling | As a transport coordinator, I want to change the van, driver or time of a booking with clash warnings, so that I can make informed changes. | AC-1: GIVEN I change a booking to Van 1 at a time Van 1 is already booked WHEN I try to save THEN saving is blocked and the clashing booking is shown AC-2: GIVEN my change triggers only a soft warning (e.g. a larger van than needed) WHEN I save THEN I must enter a reason, and the change is audit-logged AC-3: GIVEN I change a Confirmed booking's time or van WHEN I save THEN the requester is sent a 'Your trip has changed' SMS with the new details | Must | 5 | Medium | FR-23, FR-27 | Release 1 (MVP) | Draft
US-25 | EP-04 | Coordinator Review & Scheduling | As a transport coordinator, I want to decline a request with a reason, so that the requester knows why and can make other arrangements. | AC-1: GIVEN I click 'Decline' WHEN I choose a reason (No van available / Outside hours / Duplicate / Not a college trip / Other) and confirm THEN status becomes Declined and the requester receives the reason by SMS AC-2: GIVEN I choose 'Other' WHEN I try to confirm THEN a free-text reason is required | Must | 2 | Low | FR-28 | Release 1 (MVP) | Draft
US-26 | EP-04 | Coordinator Review & Scheduling | As a transport coordinator, I want to see day and week calendar views of all vans, so that I can see the whole schedule at a glance. | AC-1: GIVEN I open the day view WHEN it loads THEN each van is a row with bookings as blocks from 7:00 to 18:00, colour-coded by status, and fixed trips marked with a repeat icon AC-2: GIVEN I click a booking block WHEN it opens THEN I see its full details and can Approve/Change/Decline AC-3: GIVEN a new van is added by the administrator WHEN I open the calendar THEN the new van appears as a row with no other changes | Must | 5 | Medium | FR-29 | Release 1 (MVP) | Draft
US-27 | EP-04 | Coordinator Review & Scheduling | As a transport coordinator, I want to create a booking on behalf of someone who phoned or emailed, so that all trips are in one system. | AC-1: GIVEN I click 'New booking' WHEN I fill the same fields as the public form and choose source 'Phone' THEN the booking is created, allocated and shown with source 'Phone' AC-2: GIVEN I want to confirm straight away WHEN I tick 'Approve now' THEN it is Confirmed immediately if no clash, and the requester is notified | Must | 2 | Low | FR-30 | Release 1 (MVP) | Draft
US-28 | EP-04 | Coordinator Review & Scheduling | As a transport coordinator, I want to drag and drop a booking to another van or time on the calendar, so that changes are fast. | AC-1: GIVEN I drag a booking onto another van's row WHEN I drop it THEN the same clash checks as a manual change are applied before saving AC-2: GIVEN the drop would breach a hard constraint WHEN I drop it THEN the booking snaps back and the reason is shown | Could | 5 | Medium | FR-31 | Later | Draft
US-29 | EP-04 | Coordinator Review & Scheduling | As a transport coordinator, I want to print a daily run sheet per van, so that drivers know their trips and contacts. | AC-1: GIVEN I choose a date and van WHEN I click 'Run sheet' THEN an A4 printable/PDF sheet lists each trip's times, pickup, destination, contact name & phone, passengers and notes in time order AC-2: GIVEN there are no trips for that van and day WHEN I request the run sheet THEN it says 'No trips scheduled' | Should | 3 | Low | FR-32 | Release 2 | Draft
US-30 | EP-05 | Notifications & Requester Self-Service | As a requester, I want to receive an SMS when my request is received, confirmed, changed or declined, so that I know where things stand without calling. | AC-1: GIVEN I submit a request WHEN it is received THEN I get an SMS within 1 minute: 'Polymath Transport: request PT-2026-0142 received for Tue 12 Mar, 10:00. We'll confirm soon. View: <link>' AC-2: GIVEN a coordinator confirms my request WHEN it is Confirmed THEN I get an SMS with the van name, pickup location and time AC-3: GIVEN I also gave an email address WHEN any notification is sent THEN the same message is also emailed AC-4: GIVEN an SMS fails to send WHEN the SMS provider returns an error THEN the failure is shown on the booking for the coordinator | Must | 5 | Medium | FR-33, FR-35 | Release 1 (MVP) | Draft
US-31 | EP-05 | Notifications & Requester Self-Service | As a requester, I want to get a reminder the day before my trip, so that I'm ready on time. | AC-1: GIVEN my Confirmed trip is on Wednesday WHEN it is 3:00 pm on Tuesday THEN I receive a reminder SMS with time, pickup and van AC-2: GIVEN my trip is on Monday WHEN it is 3:00 pm on the Friday before THEN I receive the reminder | Should | 2 | Low | FR-34 | Release 2 | Draft
US-32 | EP-05 | Notifications & Requester Self-Service | As a requester, I want to check or cancel my booking using the link in my SMS, without logging in, so that I can free up the van if plans change. | AC-1: GIVEN I open the link in my SMS WHEN the page loads THEN I see my booking status and details only AC-2: GIVEN I tap 'Cancel this trip' and confirm WHEN the cancellation is saved THEN the status becomes Cancelled, the van is released, coordinators are alerted if the trip is within 24 h, and I get a cancellation SMS AC-3: GIVEN I tap 'Ask for a change' and describe it WHEN I send it THEN the request goes to a coordinator as 'Change requested'; the booking is unchanged until they act AC-4: GIVEN someone alters the link token WHEN they open it THEN they see 'Link not valid' and no booking data | Must | 5 | Medium | FR-35 | Release 1 (MVP) | Draft
US-33 | EP-05 | Notifications & Requester Self-Service | As a transport coordinator, I want to be alerted to urgent or same-day requests and late cancellations, so that I can act quickly. | AC-1: GIVEN a same-day request is submitted WHEN it is received THEN all coordinators get an in-app alert, plus SMS/email if enabled in their preferences AC-2: GIVEN a Confirmed trip is cancelled less than 24 h before departure WHEN the cancellation is saved THEN coordinators are alerted | Should | 3 | Low | FR-36 | Release 2 | Draft
US-34 | EP-05 | Notifications & Requester Self-Service | As a driver, I want to receive my trip list for the next day, so that I know where to go and when. | AC-1: GIVEN I am allocated to 3 trips tomorrow WHEN it is 4:00 pm today THEN I receive one SMS/email listing the 3 trips in time order | Could | 2 | Low | FR-37 | Later | Draft
US-35 | EP-06 | Fleet, Driver & Location Management | As a administrator, I want to add, edit and retire vans with their seats, features and home location, so that the system grows with the fleet without IT changes. | AC-1: GIVEN I add 'Van 3', 11 passenger seats, wheelchair access, home Main Campus, WOF due 01/08/2027 WHEN I save THEN Van 3 is immediately available for allocation and appears on the calendar AC-2: GIVEN I retire Van 1, which has future Confirmed bookings WHEN I try to save THEN I am warned and shown those bookings to reassign first | Must | 3 | Low | FR-38 | Release 1 (MVP) | Draft
US-36 | EP-06 | Fleet, Driver & Location Management | As a administrator, I want to add and edit locations and the travel times between them, so that new destinations can be added easily. | AC-1: GIVEN I add 'East Campus' WHEN I save THEN it appears in the form lists and I'm prompted to enter travel times to existing locations AC-2: GIVEN a travel time is missing for a pair of locations WHEN allocation needs it THEN the default travel time (e.g. 30 min) is used and the proposal is flagged 'estimated travel time' AC-3: GIVEN I deactivate a location WHEN I save THEN it disappears from the form but existing bookings keep it | Must | 3 | Low | FR-39 | Release 1 (MVP) | Draft
US-37 | EP-06 | Fleet, Driver & Location Management | As a transport coordinator, I want to block a van for servicing and be reminded before WOF, registration, service and RUC dates, so that vans are compliant and never booked when unavailable. | AC-1: GIVEN Van 2's registration expires in 14 days WHEN the daily check runs THEN coordinators and the administrator receive a reminder AC-2: GIVEN I add a maintenance block that overlaps Proposed bookings WHEN I save THEN those bookings are re-allocated; overlapping Confirmed bookings are listed for me to resolve | Must | 3 | Medium | FR-40 | Release 1 (MVP) | Draft
US-38 | EP-06 | Fleet, Driver & Location Management | As a administrator, I want to manage approved drivers with licence details and availability, so that only eligible drivers are allocated. | AC-1: GIVEN I add a driver with licence class 1 (full) expiring 01/01/2030 and availability Mon–Wed WHEN I save THEN they can be allocated to trips on Mon–Wed only AC-2: GIVEN I enter leave dates for a driver WHEN I save THEN they are not allocated on those dates, and affected Proposed trips are re-allocated | Should | 3 | Low | FR-41 | Release 2 | Draft
US-39 | EP-06 | Fleet, Driver & Location Management | As a administrator, I want to configure buffers, minimum notice, operating hours and other rules, so that the system matches how we work. | AC-1: GIVEN I change the turnaround buffer from 15 to 20 minutes WHEN I save THEN new allocations use 20 minutes, existing Confirmed bookings are unchanged, and the change is audit-logged AC-2: GIVEN I enter the 2027 term dates WHEN I save THEN fixed-trip series spanning 2027 are regenerated to match | Must | 3 | Low | FR-42, FR-12 | Release 1 (MVP) | Draft
US-40 | EP-07 | Reporting & Insights | As a member of college leadership, I want to see monthly reports of van utilisation, demand and unmet requests, so that we can decide whether to add vans. | AC-1: GIVEN I choose a month WHEN I open the utilisation report THEN I see per van: trips, hours booked, utilisation % of school hours, and the busiest day/time AC-2: GIVEN requests were declined or never allocated that month WHEN I open the demand report THEN I see how many, when, and the reasons, grouped by destination and department | Should | 5 | Medium | FR-44, FR-45 | Release 2 | Draft
US-41 | EP-07 | Reporting & Insights | As a transport coordinator, I want to export bookings and reports to Excel/CSV, so that I can share or analyse the data. | AC-1: GIVEN I am viewing a filtered list or report WHEN I click 'Export' THEN a file downloads containing exactly the filtered rows and visible columns | Should | 2 | Low | FR-46 | Release 2 | Draft
US-42 | EP-07 | Reporting & Insights | As a business manager, I want to record the odometer reading for each trip, so that we can track kilometres per van for RUC and servicing. | AC-1: GIVEN a trip is Completed WHEN the driver/coordinator enters start and end odometer THEN the kilometres are calculated, and an end reading lower than the start is rejected | Could | 3 | Low | FR-47 | Later | Draft
US-43 | EP-08 | Security, Privacy & Audit | As a transport coordinator, I want to log in securely with two-factor authentication, so that only authorised staff can manage bookings. | AC-1: GIVEN I have a Coordinator account WHEN I sign in with password and 2FA code (or college SSO) THEN I reach the dashboard AC-2: GIVEN I am idle for 30 minutes WHEN I try to act THEN I must sign in again AC-3: GIVEN I have the Viewer role WHEN I open a booking THEN I cannot approve, change or decline it | Must | 3 | Medium | FR-43, FR-48, FR-51 | Release 1 (MVP) | Draft
US-44 | EP-08 | Security, Privacy & Audit | As a privacy officer, I want to have requesters see a short privacy notice, and old personal data removed automatically, so that we meet the NZ Privacy Act 2020. | AC-1: GIVEN I open the request form WHEN I look below the Send button THEN a short notice states what is collected, why, who sees it, how long it's kept and who to contact AC-2: GIVEN the retention period is 24 months WHEN a trip is more than 24 months old THEN the requester's name, phone and email are anonymised automatically, and trip statistics are kept | Must | 3 | Medium | FR-49 | Release 1 (MVP) | Draft
US-45 | EP-08 | Security, Privacy & Audit | As a transport coordinator, I want to have every change to a booking recorded (who, what, when, why), so that we can resolve questions and disputes. | AC-1: GIVEN any user or the system changes a booking WHEN the change is saved THEN the booking's history shows the timestamp, user/'System', fields before/after and reason AC-2: GIVEN I am an Administrator WHEN I try to edit or delete history THEN no such option exists | Must | 3 | Medium | FR-50 | Release 1 (MVP) | Draft

## Requirements
Req ID | Type | Title | Description | Priority | Objective | BR ref | Stories | Source
BR-01 | Business | Single, simple request channel | Staff shall be able to request transport through one public online form, with no account or login. Name and phone number are mandatory. | Must | BO-04 |  |  | Problem statement
BR-02 | Business | Recurring fixed trips | The college shall be able to schedule known recurring trips (e.g. swimming, basketball, badminton) in advance for whole terms. | Must | BO-01 |  |  | Problem statement
BR-03 | Business | Automatic allocation | The system shall automatically propose the most efficient allocation of vans (and drivers, where applicable) for every trip. | Must | BO-01, BO-03 |  |  | Problem statement
BR-04 | Business | Coordinator control | Transport coordinators shall approve, change or decline every allocation before it is confirmed to the requester. | Must | BO-01, BO-02 |  |  | Problem statement
BR-05 | Business | Safe, clash-free scheduling | The solution shall prevent double bookings and prevent allocation of vans that are under maintenance or non-compliant. | Must | BO-02 |  |  | BA analysis (H&S)
BR-06 | Business | Keep requesters informed | Requesters shall be told the status of their request and any changes without having to contact a coordinator. | Must | BO-05 |  |  | BA analysis
BR-07 | Business | Scalable through configuration | College staff shall be able to add or change vans, drivers, locations, travel times and term dates without software changes. | Must | BO-06 |  |  | Problem statement
BR-08 | Business | Usage and demand insight | The college shall have reports on van usage and on unmet demand to support fleet decisions. | Should | BO-03 |  |  | BA analysis
BR-09 | Business | Usable by non-technical staff | The solution shall be easy to use on phones and computers by staff with low technical confidence. | Must | BO-04 |  |  | Problem statement
BR-10 | Business | Privacy and access control | Personal information shall be handled in line with the NZ Privacy Act 2020, and management functions shall be limited to authorised staff. | Must | — |  |  | Regulatory scan
BR-11 | Business | Accountability | All allocation decisions and changes shall be recorded (who, what, when, why). | Must | BO-02 |  |  | BA analysis
FR-01 | Functional | Public request form | The system shall provide a public, no-login, mobile-responsive request form reachable by URL and printable QR code. | Must |  | BR-01, BR-09 | US-01 | BA analysis
FR-02 | Functional | Mandatory & optional fields | Mandatory: requester name, phone, trip date, departure time, pickup location, destination, number of passengers, journey type, and return/collect time (unless one-way). Optional: email, department/team, purpose, special requirements, notes. | Must |  | BR-01 | US-01, US-02, US-03 | BA analysis
FR-03 | Functional | Field validation | The system shall validate NZ phone numbers (mobile and landline; stored in +64 format), reject past dates, require return time after departure, limit passengers to 1–99, and show plain-language error messages next to the field. | Must |  | BR-01, BR-09 | US-01 | BA analysis
FR-04 | Functional | Submission confirmation | On submit the system shall generate a unique reference (format PT-YYYY-NNNN), show a confirmation screen with a summary, trigger allocation (FR-16) and send an acknowledgement (FR-33). | Must |  | BR-01, BR-06 | US-01 | BA analysis
FR-05 | Functional | Location selection | Pickup and destination shall be chosen from a list of active locations, plus an 'Other address' option with a mandatory free-text address. | Must |  | BR-01, BR-07 | US-02 | BA analysis
FR-06 | Functional | Journey type | The form shall ask 'Does the van need to wait with your group?' with options: Van waits with group / Drop off and collect later / One way only. | Must |  | BR-03 | US-03 | BA analysis
FR-07 | Functional | Short-notice & out-of-hours warning | The form shall warn the requester when the trip is within the minimum notice period or outside operating hours; the request is still accepted and flagged (BRL-13). | Should |  | BR-06 | US-05 | BA analysis
FR-08 | Functional | Anti-abuse protection | The form shall use an invisible CAPTCHA/honeypot and rate limits (default 5 submissions per phone and per IP per hour), and flag first-time phone numbers (BRL-15). | Must |  | BR-10 | US-06 | BA analysis
FR-09 | Functional | Special requirements | The form shall offer tick-boxes for wheelchair access and large equipment, plus a free-text 'Anything else we should know?'. | Should |  | BR-03 | US-04 | BA analysis
FR-10 | Functional | Availability hint | After the date is chosen, the form may show a simple 'busy/free' indication by time of day, without showing other requesters' details. | Could |  | BR-01 | US-07 | BA analysis
FR-11 | Functional | Recurring series | Coordinators shall create a fixed-trip series: name, activity, contact person & phone, weekly/fortnightly pattern and day(s), times, pickup, destination, passengers, journey type, preferred van (optional), and date range or term(s). | Must |  | BR-02 | US-08 | BA analysis
FR-12 | Functional | Term & holiday calendar | The system shall hold term dates, NZ public holidays and college non-school days, and shall not generate occurrences on those days (BRL-14). | Must |  | BR-02 | US-09 | BA analysis
FR-13 | Functional | Occurrence exceptions | Coordinators shall be able to change or cancel one occurrence, or 'this and all following', without affecting other occurrences; the series contact is notified. | Must |  | BR-02, BR-06 | US-10 | BA analysis
FR-14 | Functional | Fixed-trip priority | Fixed-trip occurrences shall be allocated before ad-hoc requests (BRL-07) when the series is created and whenever the calendar changes. | Must |  | BR-02, BR-03 | US-11 | BA analysis
FR-15 | Functional | Bulk import | Coordinators may import fixed-trip series from an Excel/CSV template, with a validation report before saving. | Could |  | BR-02 | US-12 | BA analysis
FR-16 | Functional | Automatic allocation trigger | The system shall run allocation automatically on every new or changed request and every cancellation, and on demand. Result: 'Proposed' or 'Needs attention' within 5 seconds. | Must |  | BR-03 | US-13 | BA analysis
FR-17 | Functional | Hard constraints | Allocation shall enforce BRL-01 to BRL-06 without exception. | Must |  | BR-03, BR-05 | US-14, US-20 | BA analysis
FR-18 | Functional | Preference ranking | Allocation shall rank feasible options using BRL-08, with administrator-editable weights. | Must |  | BR-03 | US-15 | BA analysis
FR-19 | Functional | Allocation explanation | Each proposal shall show a plain-English reason, e.g. 'Van 2 chosen: 12 seats fits 9 passengers; already at Main Campus; Van 1 busy 9:00–11:30 (Swimming)'. | Should |  | BR-04, BR-11 | US-16 | BA analysis
FR-20 | Functional | No-fit handling | When no allocation is possible the system shall apply BRL-10 and show the alternatives to the coordinator. | Must |  | BR-03, BR-04 | US-17 | BA analysis
FR-21 | Functional | Consolidation suggestion | The system shall suggest combining compatible requests (BRL-11); the coordinator decides. | Should |  | BR-03 | US-18 | BA analysis
FR-22 | Functional | Multi-van split | The system shall propose multi-van allocations for groups larger than one van (BRL-09). | Should |  | BR-03 | US-19 | BA analysis
FR-23 | Functional | Confirmed bookings locked | The system shall never change a Confirmed booking automatically; it may only suggest changes to a coordinator. | Must |  | BR-04 | US-13, US-24 | BA analysis
FR-24 | Functional | Driver allocation | When enabled in settings, the system shall allocate an eligible driver together with the van (BRL-05). | Should |  | BR-03, BR-05 | US-21 | BA analysis
FR-25 | Functional | Coordinator dashboard | The dashboard shall show counts and lists of: Needs attention, Proposed (awaiting approval), Urgent, and Today's trips, sorted by trip date and urgency, with filters by status, van, date and location. | Must |  | BR-04 | US-22 | BA analysis
FR-26 | Functional | Approve | Coordinators shall approve single or multiple proposals in one action; status becomes Confirmed and the requester is notified. | Must |  | BR-04, BR-06 | US-23 | BA analysis
FR-27 | Functional | Change booking | Coordinators shall change van, driver, times, locations or passengers with a live clash check. A reason is required to save over a warning; hard-constraint breaches (BRL-01 to BRL-04) cannot be saved. | Must |  | BR-04, BR-05 | US-24 | BA analysis
FR-28 | Functional | Decline | Coordinators shall decline a request with a reason (pick-list plus optional text); the requester is notified. | Must |  | BR-04, BR-06 | US-25 | BA analysis
FR-29 | Functional | Calendar views | Day view (timeline per van), week view and list view, colour-coded by status, with fixed trips visually distinct. | Must |  | BR-04 | US-26 | BA analysis
FR-30 | Functional | Booking on behalf | Coordinators shall create a booking for someone who phoned or emailed, recording the source (Phone/Email/In person). | Must |  | BR-01, BR-04 | US-27 | BA analysis
FR-31 | Functional | Drag and drop | Coordinators may drag a booking to another van or time on the calendar, with the same validation as FR-27. | Could |  | BR-04 | US-28 | BA analysis
FR-32 | Functional | Daily run sheet | Printable/PDF run sheet per van (and driver) for a chosen day: times, pickup, destination, contact name & phone, passengers, notes. | Should |  | BR-04 | US-29 | BA analysis
FR-33 | Functional | Status notifications | The system shall send SMS (and email if provided) when a request is received, confirmed, changed, declined or cancelled. Message templates can be edited by the administrator. | Must |  | BR-06 | US-30 | BA analysis
FR-34 | Functional | Trip reminder | The system shall send a reminder at a configurable time on the previous school day (default 3:00 pm; Friday for Monday trips). | Should |  | BR-06 | US-31 | BA analysis
FR-35 | Functional | Secure self-service link | Each notification shall include a unique, unguessable link that lets the requester view status and cancel, or ask for a change (which goes to a coordinator), with no login. | Must |  | BR-06, BR-10 | US-32 | BA analysis
FR-36 | Functional | Coordinator alerts | Coordinators shall be alerted (in-app, plus email/SMS configurable) about urgent or same-day requests, Needs-attention items, and cancellations within 24 h of the trip. | Should |  | BR-04 | US-33 | BA analysis
FR-37 | Functional | Driver schedule | Drivers may receive their next-day schedule by SMS/email. | Could |  | BR-06 | US-34 | BA analysis
FR-38 | Functional | Vehicle register | Administrators shall add, edit and retire vans: name/fleet no., registration, passenger seats, features, home location, status (Active/Maintenance/Retired), and WOF, registration, service and RUC due dates/distances. There is no limit on the number of vans. | Must |  | BR-07, BR-05 | US-35 | BA analysis
FR-39 | Functional | Locations & travel times | Administrators shall maintain locations (name, type: Campus/Venue/Other, address, active flag) and a travel-time table (minutes) between locations, with a default time for unlisted pairs. | Must |  | BR-07 | US-36 | BA analysis
FR-40 | Functional | Maintenance & compliance | Coordinators shall block a van for a period (e.g. servicing). The system shall remind them before compliance dates (default 14 days) and exclude the van from allocation from the expiry date. | Must |  | BR-05 | US-37, US-20 | BA analysis
FR-41 | Functional | Driver register | Administrators shall maintain drivers: name, phone, licence class and expiry, usual availability, leave dates, active flag. | Should |  | BR-05, BR-07 | US-38 | BA analysis
FR-42 | Functional | Settings | Administrators shall configure buffers, minimum notice, operating hours, reminder time, rate limits, manual-review triggers, preference weights and data retention period. | Must |  | BR-07 | US-39 | BA analysis
FR-43 | Functional | User management | Administrators shall create and deactivate staff accounts with the roles Coordinator, Administrator or Viewer. | Must |  | BR-10 | US-43 | BA analysis
FR-44 | Functional | Utilisation report | Per van and period: trips, hours booked vs available (school hours), utilisation %, and busiest days/times. | Should |  | BR-08 | US-40 | BA analysis
FR-45 | Functional | Demand & unmet-demand report | Requests by destination, department, journey type and source; declined or unfulfilled requests with reasons. | Should |  | BR-08 | US-40 | BA analysis
FR-46 | Functional | Export | Any list or report can be exported to Excel/CSV. | Should |  | BR-08 | US-41 | BA analysis
FR-47 | Functional | Odometer capture | Start/end odometer may be recorded per trip to calculate kilometres per van (supports RUC and servicing). | Could |  | BR-08 | US-42 | BA analysis
FR-48 | Functional | Staff authentication | Staff users shall sign in with two-factor authentication (or college single sign-on if available); sessions time out after 30 minutes idle. | Must |  | BR-10 | US-43 | BA analysis
FR-49 | Functional | Privacy notice & retention | The form shall show a short privacy notice. Requester personal details shall be anonymised automatically after the retention period (default 24 months after the trip). | Must |  | BR-10 | US-44 | BA analysis
FR-50 | Functional | Audit trail | The system shall log every create, change, approve, decline, cancel and automatic allocation (user/system, timestamp, before/after, reason). The log is read-only. | Must |  | BR-11 | US-45 | BA analysis
FR-51 | Functional | Role-based access | The public can only submit requests and see their own booking via its secure link; Viewers see calendars and reports; Coordinators manage bookings; Administrators also manage settings and users. | Must |  | BR-10 | US-43 | BA analysis
NFR-01 | Non-functional – Usability | Usability | A first-time requester can complete the form without help. [Measure: In a test with 5 staff, 5 of 5 complete it unaided; median 2 minutes or less] | Must |  |  |  | BA analysis
NFR-02 | Non-functional – Usability | Usability | Plain language throughout; no technical jargon; one question per field; the form fits on one scrolling page. [Measure: Reviewed against NZ plain-language guidance; at most 12 visible fields by default] | Must |  |  |  | BA analysis
NFR-03 | Non-functional – Accessibility | Accessibility | Conforms to WCAG 2.2 Level AA (contrast, keyboard use, screen-reader labels, large touch targets). [Measure: Accessibility audit before go-live] | Must |  |  |  | BA analysis
NFR-04 | Non-functional – Compatibility | Compatibility | Works on phones (360 px wide and up), tablets and desktops; latest 2 versions of Chrome, Safari, Edge and Firefox; iOS and Android. [Measure: Cross-device test pass] | Must |  |  |  | BA analysis
NFR-05 | Non-functional – Performance | Performance | Pages load in 3 seconds or less on 4G; allocation completes in 5 seconds or less. [Measure: Measured at 20 vans / 500 bookings per week] | Must |  |  |  | BA analysis
NFR-06 | Non-functional – Availability | Availability | 99.5% availability 06:30–19:00 Mon–Fri (NZ time); maintenance outside these hours. [Measure: Monthly uptime report] | Should |  |  |  | BA analysis
NFR-07 | Non-functional – Scalability | Scalability | Supports at least 20 vans, 50 locations, 20 staff users and 5 years of history with no code change. [Measure: Load/volume test] | Must |  |  |  | BA analysis
NFR-08 | Non-functional – Security | Security | HTTPS (TLS 1.2+), encryption at rest, OWASP Top 10 controls, 2FA for staff, secure unguessable self-service tokens. [Measure: Security review / penetration test before go-live] | Must |  |  |  | BA analysis
NFR-09 | Non-functional – Privacy | Privacy | Complies with NZ Privacy Act 2020 (collection limited to what is needed, notice, security, access/correction, retention, breach notification). [Measure: Privacy Officer sign-off; privacy impact assessment] | Must |  |  |  | BA analysis
NFR-10 | Non-functional – Data residency | Data residency | Data hosted in New Zealand or Australia unless the college agrees otherwise. [Measure: Hosting contract (confirm – Q-13)] | Should |  |  |  | BA analysis
NFR-11 | Non-functional – Resilience | Resilience | Daily backups; RPO 24 h; RTO 1 school day; restore tested each term. [Measure: Restore test record] | Must |  |  |  | BA analysis
NFR-12 | Non-functional – Localisation | Localisation | NZ time zone including daylight saving; dates DD/MM/YYYY; times shown as '10:30 am'; NZ English. [Measure: Test cases across DST changeover] | Must |  |  |  | BA analysis
NFR-13 | Non-functional – Maintainability | Maintainability | Vans, drivers, locations, travel times, term dates, templates and rules are changed through admin screens, with no developer needed. [Measure: Admin walkthrough (BO-06)] | Must |  |  |  | BA analysis
NFR-14 | Non-functional – Supportability | Supportability | Context help on each screen; one-page quick guide for requesters; coordinator training of 1 hour or less. [Measure: Training feedback] | Should |  |  |  | BA analysis
NFR-15 | Non-functional – Auditability | Auditability | Audit records cannot be edited or deleted by any user role and are kept for at least the data retention period. [Measure: Security test] | Must |  |  |  | BA analysis

## Business Rules
Rule ID | Type | Rule | Default / configurable
BRL-01 | Hard constraint | A van (or driver) can never be allocated to two trips whose occupancy windows overlap. Occupancy window = departure time − preparation buffer − travel time from the van's previous location, up to trip end + turnaround buffer. | Prep buffer 10 min; turnaround 15 min
BRL-02 | Hard constraint | Van passenger seats (excluding the driver) must be at least the number of passengers. | —
BRL-03 | Hard constraint | The van must be 'Active', not in a maintenance block, and have WOF and registration valid on the trip date. | —
BRL-04 | Hard constraint | The van must have every feature the trip needs (e.g. wheelchair access, tow bar, large luggage space). | —
BRL-05 | Hard constraint | If drivers are allocated by the system: the driver must be active and available, hold a valid licence of the required class, and not exceed the maximum driving time per day. | Max 6 h/day (TBC with H&S)
BRL-06 | Occupancy by journey type | 'Van waits with group': the van is occupied from departure to return. 'Drop off & collect later': two separate legs (out and back), and the van is free in between. 'One way': outbound leg only. | —
BRL-07 | Priority | Allocation order: (1) Confirmed bookings are never moved; (2) fixed-trip occurrences; (3) ad-hoc requests in order of trip date, then submission time; (4) a coordinator may set a request to 'High priority'. | —
BRL-08 | Preference (soft) | Among feasible vans, prefer: (a) the smallest van that fits (keeps large vans free for large groups); (b) the van already at or nearest the pickup (least empty running); (c) the fixed trip's preferred van; (d) the least-used van this week (balances wear). | Weights editable by the administrator
BRL-09 | Split | If passengers exceed the largest single van, propose the fewest vans that together fit the group, all departing together. | —
BRL-10 | No fit | If no feasible allocation exists, set status 'Needs attention', list the conflicting bookings, and suggest up to 3 alternatives: nearest free time within ±60 min, a split across vans, or a swap involving unconfirmed bookings only. | Search window ±60 min
BRL-11 | Consolidation | If two requests share a destination, depart within 15 min of each other and fit together, suggest combining them. Never merge automatically. | 15 min window
BRL-12 | Re-optimisation | When a booking is cancelled or changed, re-run allocation for unconfirmed (Proposed / Needs attention) bookings only. | —
BRL-13 | Notice & hours | Requests with less than the minimum notice, or outside operating hours, are accepted but flagged 'Urgent' / 'Out of hours' for the coordinator. | 24 h notice; Mon–Fri 07:00–18:00
BRL-14 | Calendar | Fixed-trip occurrences are not generated on school holidays, NZ public holidays or college non-school days (e.g. teacher-only days). | Term calendar maintained by admin
BRL-15 | Manual review triggers | Requests with an 'Other' (unlisted) address, wheelchair needs, or from a phone number never seen before are always set to 'Needs attention', even if a van is found. | Each trigger can be switched on/off

## RTM
Req ID | Title | Type | Priority | Objective | BR ref | Epic | User stories | Test case IDs | Test status | Delivery status | Release | Regulatory link | Notes
FR-01 | Public request form | Functional | Must | BO-04 | BR-01, BR-09 | EP-01 | US-01 | TC-US-01-1, TC-US-01-2, TC-US-01-3, TC-US-01-4, TC-US-01-5 | Not started | Backlog | Release 1 (MVP)
FR-02 | Mandatory & optional fields | Functional | Must | BO-04 | BR-01 | EP-01 | US-01, US-02, US-03 | TC-US-01-1, TC-US-01-2, TC-US-01-3, TC-US-01-4, TC-US-01-5, TC-US-02-1, TC-US-02-2, TC-US-02-3, TC-US-03-1, TC-US-03-2, TC-US-03-3, TC-US-03-4 | Not started | Backlog | Release 1 (MVP)
FR-03 | Field validation | Functional | Must | BO-04 | BR-01, BR-09 | EP-01 | US-01 | TC-US-01-1, TC-US-01-2, TC-US-01-3, TC-US-01-4, TC-US-01-5 | Not started | Backlog | Release 1 (MVP)
FR-04 | Submission confirmation | Functional | Must | BO-04, BO-05 | BR-01, BR-06 | EP-01 | US-01 | TC-US-01-1, TC-US-01-2, TC-US-01-3, TC-US-01-4, TC-US-01-5 | Not started | Backlog | Release 1 (MVP)
FR-05 | Location selection | Functional | Must | BO-04, BO-06 | BR-01, BR-07 | EP-01 | US-02 | TC-US-02-1, TC-US-02-2, TC-US-02-3 | Not started | Backlog | Release 1 (MVP)
FR-06 | Journey type | Functional | Must | BO-01, BO-03 | BR-03 | EP-01 | US-03 | TC-US-03-1, TC-US-03-2, TC-US-03-3, TC-US-03-4 | Not started | Backlog | Release 1 (MVP)
FR-07 | Short-notice & out-of-hours warning | Functional | Should | BO-05 | BR-06 | EP-01 | US-05 | TC-US-05-1, TC-US-05-2, TC-US-05-3 | Not started | Backlog | Release 2
FR-08 | Anti-abuse protection | Functional | Must | — | BR-10 | EP-01 | US-06 | TC-US-06-1, TC-US-06-2, TC-US-06-3 | Not started | Backlog | Release 1 (MVP) | Privacy Act 2020
FR-09 | Special requirements | Functional | Should | BO-01, BO-03 | BR-03 | EP-01 | US-04 | TC-US-04-1, TC-US-04-2, TC-US-04-3 | Not started | Backlog | Release 2
FR-10 | Availability hint | Functional | Could | BO-04 | BR-01 | EP-01 | US-07 | TC-US-07-1, TC-US-07-2 | Not started | Backlog | Later
FR-11 | Recurring series | Functional | Must | BO-01 | BR-02 | EP-02 | US-08 | TC-US-08-1, TC-US-08-2, TC-US-08-3 | Not started | Backlog | Release 1 (MVP)
FR-12 | Term & holiday calendar | Functional | Must | BO-01 | BR-02 | EP-02 | US-09 | TC-US-09-1, TC-US-09-2, TC-US-09-3 | Not started | Backlog | Release 1 (MVP)
FR-13 | Occurrence exceptions | Functional | Must | BO-01, BO-05 | BR-02, BR-06 | EP-02 | US-10 | TC-US-10-1, TC-US-10-2 | Not started | Backlog | Release 1 (MVP)
FR-14 | Fixed-trip priority | Functional | Must | BO-01, BO-03 | BR-02, BR-03 | EP-02 | US-11 | TC-US-11-1, TC-US-11-2 | Not started | Backlog | Release 1 (MVP)
FR-15 | Bulk import | Functional | Could | BO-01 | BR-02 | EP-02 | US-12 | TC-US-12-1, TC-US-12-2 | Not started | Backlog | Later
FR-16 | Automatic allocation trigger | Functional | Must | BO-01, BO-03 | BR-03 | EP-03 | US-13 | TC-US-13-1, TC-US-13-2, TC-US-13-3 | Not started | Backlog | Release 1 (MVP)
FR-17 | Hard constraints | Functional | Must | BO-01, BO-02, BO-03 | BR-03, BR-05 | EP-03 | US-14, US-20 | TC-US-14-1, TC-US-14-2, TC-US-14-3, TC-US-20-1, TC-US-20-2, TC-US-20-3 | Not started | Backlog | Release 1 (MVP) | HSWA 2015 / land transport
FR-18 | Preference ranking | Functional | Must | BO-01, BO-03 | BR-03 | EP-03 | US-15 | TC-US-15-1, TC-US-15-2, TC-US-15-3 | Not started | Backlog | Release 1 (MVP)
FR-19 | Allocation explanation | Functional | Should | BO-01, BO-02 | BR-04, BR-11 | EP-03 | US-16 | TC-US-16-1, TC-US-16-2 | Not started | Backlog | Release 2
FR-20 | No-fit handling | Functional | Must | BO-01, BO-02, BO-03 | BR-03, BR-04 | EP-03 | US-17 | TC-US-17-1, TC-US-17-2, TC-US-17-3 | Not started | Backlog | Release 1 (MVP)
FR-21 | Consolidation suggestion | Functional | Should | BO-01, BO-03 | BR-03 | EP-03 | US-18 | TC-US-18-1, TC-US-18-2, TC-US-18-3 | Not started | Backlog | Release 2
FR-22 | Multi-van split | Functional | Should | BO-01, BO-03 | BR-03 | EP-03 | US-19 | TC-US-19-1, TC-US-19-2 | Not started | Backlog | Release 2
FR-23 | Confirmed bookings locked | Functional | Must | BO-01, BO-02 | BR-04 | EP-03 | US-13, US-24 | TC-US-13-1, TC-US-13-2, TC-US-13-3, TC-US-24-1, TC-US-24-2, TC-US-24-3 | Not started | Backlog | Release 1 (MVP)
FR-24 | Driver allocation | Functional | Should | BO-01, BO-02, BO-03 | BR-03, BR-05 | EP-03 | US-21 | TC-US-21-1, TC-US-21-2, TC-US-21-3 | Not started | Backlog | Release 2 | HSWA 2015 / land transport
FR-25 | Coordinator dashboard | Functional | Must | BO-01, BO-02 | BR-04 | EP-04 | US-22 | TC-US-22-1, TC-US-22-2, TC-US-22-3 | Not started | Backlog | Release 1 (MVP)
FR-26 | Approve | Functional | Must | BO-01, BO-02, BO-05 | BR-04, BR-06 | EP-04 | US-23 | TC-US-23-1, TC-US-23-2, TC-US-23-3 | Not started | Backlog | Release 1 (MVP)
FR-27 | Change booking | Functional | Must | BO-01, BO-02 | BR-04, BR-05 | EP-04 | US-24 | TC-US-24-1, TC-US-24-2, TC-US-24-3 | Not started | Backlog | Release 1 (MVP) | HSWA 2015 / land transport
FR-28 | Decline | Functional | Must | BO-01, BO-02, BO-05 | BR-04, BR-06 | EP-04 | US-25 | TC-US-25-1, TC-US-25-2 | Not started | Backlog | Release 1 (MVP)
FR-29 | Calendar views | Functional | Must | BO-01, BO-02 | BR-04 | EP-04 | US-26 | TC-US-26-1, TC-US-26-2, TC-US-26-3 | Not started | Backlog | Release 1 (MVP)
FR-30 | Booking on behalf | Functional | Must | BO-01, BO-02, BO-04 | BR-01, BR-04 | EP-04 | US-27 | TC-US-27-1, TC-US-27-2 | Not started | Backlog | Release 1 (MVP)
FR-31 | Drag and drop | Functional | Could | BO-01, BO-02 | BR-04 | EP-04 | US-28 | TC-US-28-1, TC-US-28-2 | Not started | Backlog | Later
FR-32 | Daily run sheet | Functional | Should | BO-01, BO-02 | BR-04 | EP-04 | US-29 | TC-US-29-1, TC-US-29-2 | Not started | Backlog | Release 2
FR-33 | Status notifications | Functional | Must | BO-05 | BR-06 | EP-05 | US-30 | TC-US-30-1, TC-US-30-2, TC-US-30-3, TC-US-30-4 | Not started | Backlog | Release 1 (MVP)
FR-34 | Trip reminder | Functional | Should | BO-05 | BR-06 | EP-05 | US-31 | TC-US-31-1, TC-US-31-2 | Not started | Backlog | Release 2
FR-35 | Secure self-service link | Functional | Must | BO-05 | BR-06, BR-10 | EP-05 | US-32 | TC-US-32-1, TC-US-32-2, TC-US-32-3, TC-US-32-4 | Not started | Backlog | Release 1 (MVP) | Privacy Act 2020
FR-36 | Coordinator alerts | Functional | Should | BO-01, BO-02 | BR-04 | EP-05 | US-33 | TC-US-33-1, TC-US-33-2 | Not started | Backlog | Release 2
FR-37 | Driver schedule | Functional | Could | BO-05 | BR-06 | EP-05 | US-34 | TC-US-34-1 | Not started | Backlog | Later
FR-38 | Vehicle register | Functional | Must | BO-02, BO-06 | BR-07, BR-05 | EP-06 | US-35 | TC-US-35-1, TC-US-35-2 | Not started | Backlog | Release 1 (MVP) | HSWA 2015 / land transport
FR-39 | Locations & travel times | Functional | Must | BO-06 | BR-07 | EP-06 | US-36 | TC-US-36-1, TC-US-36-2, TC-US-36-3 | Not started | Backlog | Release 1 (MVP)
FR-40 | Maintenance & compliance | Functional | Must | BO-02 | BR-05 | EP-03 | US-37, US-20 | TC-US-37-1, TC-US-37-2, TC-US-20-1, TC-US-20-2, TC-US-20-3 | Not started | Backlog | Release 1 (MVP) | HSWA 2015 / land transport
FR-41 | Driver register | Functional | Should | BO-02, BO-06 | BR-05, BR-07 | EP-06 | US-38 | TC-US-38-1, TC-US-38-2 | Not started | Backlog | Release 2 | HSWA 2015 / land transport
FR-42 | Settings | Functional | Must | BO-06 | BR-07 | EP-06 | US-39 | TC-US-39-1, TC-US-39-2 | Not started | Backlog | Release 1 (MVP)
FR-43 | User management | Functional | Must | — | BR-10 | EP-08 | US-43 | TC-US-43-1, TC-US-43-2, TC-US-43-3 | Not started | Backlog | Release 1 (MVP) | Privacy Act 2020
FR-44 | Utilisation report | Functional | Should | BO-03 | BR-08 | EP-07 | US-40 | TC-US-40-1, TC-US-40-2 | Not started | Backlog | Release 2
FR-45 | Demand & unmet-demand report | Functional | Should | BO-03 | BR-08 | EP-07 | US-40 | TC-US-40-1, TC-US-40-2 | Not started | Backlog | Release 2
FR-46 | Export | Functional | Should | BO-03 | BR-08 | EP-07 | US-41 | TC-US-41-1 | Not started | Backlog | Release 2
FR-47 | Odometer capture | Functional | Could | BO-03 | BR-08 | EP-07 | US-42 | TC-US-42-1 | Not started | Backlog | Later
FR-48 | Staff authentication | Functional | Must | — | BR-10 | EP-08 | US-43 | TC-US-43-1, TC-US-43-2, TC-US-43-3 | Not started | Backlog | Release 1 (MVP) | Privacy Act 2020
FR-49 | Privacy notice & retention | Functional | Must | — | BR-10 | EP-08 | US-44 | TC-US-44-1, TC-US-44-2 | Not started | Backlog | Release 1 (MVP) | Privacy Act 2020
FR-50 | Audit trail | Functional | Must | BO-02 | BR-11 | EP-08 | US-45 | TC-US-45-1, TC-US-45-2 | Not started | Backlog | Release 1 (MVP)
FR-51 | Role-based access | Functional | Must | — | BR-10 | EP-08 | US-43 | TC-US-43-1, TC-US-43-2, TC-US-43-3 | Not started | Backlog | Release 1 (MVP) | Privacy Act 2020
NFR-01 | A first-time requester can complete the form without help. | Non-functional | Must | BO-04 | BR-09 | All | — | TC-NFR-01 | Not started | Backlog | Release 1 (MVP)
NFR-02 | Plain language throughout; no technical jargon; one question | Non-functional | Must | BO-04 | BR-09 | All | — | TC-NFR-02 | Not started | Backlog | Release 1 (MVP)
NFR-03 | Conforms to WCAG 2.2 Level AA (contrast, keyboard use, scree | Non-functional | Must | BO-04 | BR-09 | All | — | TC-NFR-03 | Not started | Backlog | Release 1 (MVP)
NFR-04 | Works on phones (360 px wide and up), tablets and desktops; | Non-functional | Must | BO-04 | BR-09 | All | — | TC-NFR-04 | Not started | Backlog | Release 1 (MVP)
NFR-05 | Pages load in 3 seconds or less on 4G; allocation completes | Non-functional | Must | — | BR-07 | All | — | TC-NFR-05 | Not started | Backlog | Release 1 (MVP)
NFR-06 | 99.5% availability 06:30–19:00 Mon–Fri (NZ time); maintenanc | Non-functional | Should | — | BR-07 | All | — | TC-NFR-06 | Not started | Backlog | Release 2
NFR-07 | Supports at least 20 vans, 50 locations, 20 staff users and | Non-functional | Must | — | BR-07 | All | — | TC-NFR-07 | Not started | Backlog | Release 1 (MVP)
NFR-08 | HTTPS (TLS 1.2+), encryption at rest, OWASP Top 10 controls, | Non-functional | Must | — | BR-10 | All | — | TC-NFR-08 | Not started | Backlog | Release 1 (MVP) | Privacy Act 2020
NFR-09 | Complies with NZ Privacy Act 2020 (collection limited to wha | Non-functional | Must | — | BR-10 | All | — | TC-NFR-09 | Not started | Backlog | Release 1 (MVP) | Privacy Act 2020
NFR-10 | Data hosted in New Zealand or Australia unless the college a | Non-functional | Should | — | BR-10 | All | — | TC-NFR-10 | Not started | Backlog | Release 2
NFR-11 | Daily backups; RPO 24 h; RTO 1 school day; restore tested ea | Non-functional | Must | — | BR-07 | All | — | TC-NFR-11 | Not started | Backlog | Release 1 (MVP)
NFR-12 | NZ time zone including daylight saving; dates DD/MM/YYYY; ti | Non-functional | Must | — | BR-07 | All | — | TC-NFR-12 | Not started | Backlog | Release 1 (MVP)
NFR-13 | Vans, drivers, locations, travel times, term dates, template | Non-functional | Must | — | BR-07 | All | — | TC-NFR-13 | Not started | Backlog | Release 1 (MVP)
NFR-14 | Context help on each screen; one-page quick guide for reques | Non-functional | Should | — | BR-07 | All | — | TC-NFR-14 | Not started | Backlog | Release 2
NFR-15 | Audit records cannot be edited or deleted by any user role a | Non-functional | Must | — | BR-10 | All | — | TC-NFR-15 | Not started | Backlog | Release 1 (MVP)

## Open Questions
ID | Question | Why it matters | Owner | Affects | Answer | Status
Q-01 | Who drives the vans – dedicated drivers, or the staff member who requests the trip? What licence/endorsement is required? | Decides whether driver allocation (FR-24, US-21) is needed in Release 1. | Project Sponsor / H&S | FR-24, FR-41, BRL-05 |  | Open
Q-02 | What exactly are the '3 school destinations' – college campuses, partner schools, or activity venues? Please list all regular locations. | Location list and travel-time table. | Transport Coordinators | FR-05, FR-39 |  | Open
Q-03 | Seat capacity (excluding driver) and special features of each van? | Capacity rules and the 'smallest van' preference. | Business Manager | BRL-02, BRL-08 |  | Open
Q-04 | Minimum notice period and operating hours? Are weekend trips allowed? | Default settings and urgent flag. | Transport Coordinators | BRL-13 |  | Open
Q-05 | Should fixed-trip occurrences be auto-confirmed, or approved like other requests? | Coordinator workload vs control. | Transport Coordinators | FR-14, FR-26 |  | Open
Q-06 | Is the name + phone public form enough, or should we check college email addresses / send an SMS code? | Abuse risk vs ease of use. | Project Sponsor / Privacy Officer | FR-08 |  | Open
Q-07 | Is SMS budget approved? Expected monthly requests? | Notification channel and cost. | Business Manager | FR-33, FR-34 |  | Open
Q-08 | When requests clash, who has priority beyond 'fixed trips first' (e.g. by department or year level)? | Priority rules. | Project Sponsor | BRL-07 |  | Open
Q-09 | Does the college use a student management / SSO system we should integrate with (staff directory, term dates)? | Integration scope and login method. | IT Support | FR-12, FR-48 |  | Open
Q-10 | How long should request records be kept (default proposed: 24 months)? | Retention setting. | Privacy Officer | FR-49 |  | Open
Q-11 | Do coordinators need to approve from their phones while away from a desk? | Mobile design of coordinator screens. | Transport Coordinators | NFR-04 |  | Open
Q-12 | Do trips need a passenger (student) list for H&S/EOTC purposes? | Significant privacy and scope impact. | H&S / EOTC Coordinator | Scope |  | Open
Q-13 | Hosting preference, budget, and build vs buy (off-the-shelf fleet booking tools exist)? | Solution approach and data residency. | Project Sponsor / IT | NFR-10, R-08 |  | Open
Q-14 | For fixed trips, does the van usually wait at the venue, or drop off and return later? | The biggest efficiency lever: a van that drops off and returns can serve other trips in between. | Sports Coordinator | BRL-06, FR-06 |  | Open

## Risks
ID | Risk | Likelihood | Impact | Mitigation | Owner | Status
R-01 | Staff keep booking informally (low adoption) | Medium | High | QR-code posters, one-minute form, coordinators redirect informal requests to the form, and leadership endorsement |  | Open
R-02 | Spam or fake submissions on the public form | Medium | Medium | CAPTCHA/honeypot, rate limits, first-time-phone review (BRL-15); every request needs coordinator approval anyway |  | Open
R-03 | Inaccurate travel times cause late trips | Medium | Medium | Review travel times after month 1 using coordinator feedback; buffers configurable |  | Open
R-04 | Coordinators don't trust automatic allocation | Low | High | Plain-English explanations (FR-19); coordinators approve everything; tune rules in pilot |  | Open
R-05 | SMS costs higher than expected | Low | Low | Monitor volume; combine fixed-trip confirmations; email fallback |  | Open
R-06 | Privacy breach of requester data | Low | High | Minimal data, 2FA, encryption, retention/anonymisation, privacy impact assessment |  | Open
R-07 | Vehicle compliance dates not kept up to date | Medium | High | Reminders (FR-40); named data owner (D-03); monthly check |  | Open
R-08 | Custom build costs more than an off-the-shelf product | Medium | Medium | Run a build-vs-buy evaluation against this specification before committing |  | Open