## Read Me
PolymathTransit – User Stories, Backlog & Traceability
Version | 0.2
Date | 30/09/2026
Status | DRAFT – updated with stakeholder answers, for review
Author | Srimal
Companion document | PolymathTransit_Requirements_Specification_v0.2.docx
Sheet | Contents
Epics | Epic summary with story count, points and T-shirt size
User Stories | Full backlog with acceptance criteria (Given/When/Then), priority, points, complexity, status
Requirements | Catalogue of business, functional and non-functional requirements
Business Rules | Allocation rules the engine must apply
RTM | Traceability: objective → BR → FR → story → test case, with test & delivery status
Open Questions | Questions to resolve before design, with owner and status
Risks | Risk register
Priorities | MoSCoW – Must (Release 1 MVP), Should (Release 2), Could (later)
Story points | Indicative Fibonacci estimates (confidence Low, ±60%) – to be re-estimated by the delivery team

## Epics
Epic ID | Epic | Theme | Description | Business value | Stories | Points | T-shirt
EP-01 | Transport Request (Public Form) | T1 – Easy access for staff | A public, mobile-friendly form where staff request a van with minimal typing. | One channel for all requests; form completed in 2 minutes or less (BO-04). | 7 | 23 | L
EP-02 | Fixed & Recurring Trips | T2 – Efficient, automated scheduling | Set up regular trips once per term; occurrences are booked automatically, and school/public holidays are skipped. | Known commitments always covered; removes weekly re-booking (BO-01). | 5 | 19 | M
EP-03 | Automatic Allocation | T2 – Efficient, automated scheduling | Rules engine that proposes the best van for each trip within hard constraints (capacity, availability, contracted hours, breaks) and explains why. | Most allocations approved without change; zero double bookings (BO-01, BO-02). | 8 | 37 | L
EP-04 | Coordinator Review & Scheduling | T2 – Efficient, automated scheduling | Dashboard, approvals, changes, calendar and run sheets for coordinators. | Coordinators stay in control with far less effort (BO-01, BO-05). | 8 | 30 | L
EP-05 | Notifications & Requester Self-Service | T1 – Easy access for staff | SMS/email updates and a secure no-login link to check or cancel a booking. | Requesters always know where they stand; cancellations free vans quickly (BO-05). | 5 | 18 | M
EP-06 | Fleet, Driver & Location Management | T3 – Safe, scalable and accountable operation | Maintain vans, drivers, locations, travel times, term dates and rules without IT help. | The system scales with the fleet; compliance dates are never missed (BO-02, BO-06). | 5 | 14 | M
EP-07 | Reporting & Insights | T3 – Safe, scalable and accountable operation | Utilisation, demand and unmet-request reports; exports. | Evidence-based fleet decisions (BO-03). | 3 | 10 | M
EP-08 | Security, Privacy & Audit | T3 – Safe, scalable and accountable operation | Secure staff login, privacy compliance and a complete change history. | Personal information protected; decisions traceable (BR-10, BR-11). | 3 | 9 | M
EP-09 | Multi-stop Route Optimisation & Maps | T2 – Efficient, automated scheduling | Combine requests into shared multi-stop routes, fill gaps between legs, optimise whole days, and show routes on a map, using map-based travel times. | Fewer paid van hours and less empty running for the same demand (BO-07, BO-03). | 9 | 44 | XL
TOTAL

## User Stories
Story ID | Epic | Epic name | User story | Acceptance criteria | Priority | Points | Complexity | Traces to (FR) | Target release | Status | Notes
US-01 | EP-01 | Transport Request (Public Form) | As a teacher, I want to request a van from a simple web form on my phone without logging in, so that I can book transport in under two minutes, wherever I am. | AC-1: GIVEN I open the request form link or scan the QR code on my phone WHEN the page loads THEN I see a single page with plain-language questions and no login or sign-up prompt AC-2: GIVEN I leave 'Your name' or 'Phone number' empty WHEN I tap 'Send request' THEN the form is not sent and shows 'Please enter your name' / 'Please enter a phone number' next to the field AC-3: GIVEN I enter 021 123 4567 or (09) 123 4567 WHEN I tap 'Send request' THEN the number is accepted and stored as +64211234567 / +6491234567 AC-4: GIVEN I enter a trip date in the past, or a return time before the departure time WHEN I tap 'Send request' THEN a plain-language error explains what to fix and the form is not sent AC-5: GIVEN all mandatory fields are valid WHEN I tap 'Send request' THEN within 3 seconds I see 'Request received' with a reference (e.g. PT-2026-0142) and a summary of my trip | Must | 5 | Medium | FR-01, FR-02, FR-03, FR-04 | Release 1 (MVP) | Draft
US-02 | EP-01 | Transport Request (Public Form) | As a requester, I want to choose my pickup and destination from a list of branches and venues, or type any address, so that I can book trips to our branches and for errands without typing full addresses. | AC-1: GIVEN the administrator has 3 branches and 4 venues saved WHEN I open the pickup or destination field THEN I see 'Our branches' first, then 'Venues', and can type any other address AC-2: GIVEN I start typing an address WHEN I have typed 4 or more characters THEN matching NZ addresses are suggested and I can pick one AC-3: GIVEN the address I typed cannot be found WHEN I submit THEN the request is accepted and set to 'Needs attention' with the reason 'Address not found – check' | Must | 3 | Low | FR-02, FR-05 | Release 1 (MVP) | Draft
US-03 | EP-01 | Transport Request (Public Form) | As a requester, I want to say how many people are travelling and whether I need a return trip, so that a van with enough seats is planned and the van can do other jobs while I don't need it. | AC-1: GIVEN I am on the form WHEN I answer 'Do you need a return trip?' with 'Yes' THEN a mandatory 'Return pickup time' field and an optional tick-box 'Van must stay with us' appear AC-2: GIVEN I don't tick 'Van must stay with us' WHEN I submit THEN the van may be scheduled for other jobs between my drop-off and return pickup (BRL-06) AC-3: GIVEN the largest van has 12 passenger seats WHEN I enter 20 passengers THEN I see 'This group needs more than one van – we'll arrange this' and can still submit AC-4: GIVEN I enter 0 or more than 99 passengers WHEN I submit THEN I see 'Please enter a number between 1 and 99' | Must | 3 | Medium | FR-02, FR-06 | Release 1 (MVP) | Draft
US-04 | EP-01 | Transport Request (Public Form) | As a requester, I want to tell the coordinator about special requirements such as wheelchair access or sports gear, so that a suitable van is provided. | AC-1: GIVEN I tick 'Wheelchair access needed' WHEN allocation runs THEN only vans with the wheelchair-access feature are considered and the request is set to 'Needs attention' for a coordinator check AC-2: GIVEN I tick 'Large equipment' WHEN allocation runs THEN only vans with large-luggage capacity are considered AC-3: GIVEN I type in 'Anything else we should know?' WHEN a coordinator opens the request THEN the note is shown prominently on the request | Should | 2 | Low | FR-09 | Release 2 | Draft
US-05 | EP-01 | Transport Request (Public Form) | As a requester, I want to be warned if I'm booking at short notice or outside operating hours, so that I know my request might not be possible and can make a backup plan. | AC-1: GIVEN the minimum notice is 24 hours WHEN I choose a trip starting in 5 hours THEN I see 'Short notice – we'll try, but can't guarantee a van. For urgent help call <coordinator number>' and can still submit AC-2: GIVEN the request is submitted at short notice WHEN a coordinator views the dashboard THEN the request shows an 'Urgent' tag and sorts to the top AC-3: GIVEN operating hours are Mon–Fri 07:00–18:00 WHEN I choose Saturday 09:00 THEN I see an 'Outside normal hours' warning, and the request is flagged 'Out of hours' | Should | 2 | Low | FR-07 | Release 2 | Draft
US-06 | EP-01 | Transport Request (Public Form) | As a transport coordinator, I want to have the public form protected against spam and misuse, so that I only deal with genuine requests. | AC-1: GIVEN an automated script fills the hidden honeypot field or fails the invisible CAPTCHA WHEN it submits THEN the request is rejected silently and not shown to coordinators AC-2: GIVEN a phone number has already made 5 submissions in the past hour WHEN a 6th is submitted THEN it is blocked with 'Too many requests – please call the transport office' AC-3: GIVEN a phone number has never been used before WHEN the request is submitted THEN it is tagged 'New requester' and set to 'Needs attention' | Must | 3 | Medium | FR-08 | Release 1 (MVP) | Draft
US-07 | EP-01 | Transport Request (Public Form) | As a requester, I want to see roughly which times are free on my chosen date, so that I can choose a time that is likely to be available. | AC-1: GIVEN Van 1 and Van 2 are both booked 9:00–11:00 on 12/03/2027 WHEN I choose 12/03/2027 on the form THEN I see 9:00–11:00 marked 'Busy' and other school hours marked 'Likely free' AC-2: GIVEN availability is shown WHEN I look at busy periods THEN no details of other bookings (names, destinations) are visible | Could | 5 | Medium | FR-10 | Later | Draft
US-08 | EP-02 | Fixed & Recurring Trips | As a transport coordinator, I want to set up a recurring fixed trip (e.g. Swimming, every Tuesday 10:00–12:00, Terms 1–4), so that these trips are booked automatically without re-entering them. | AC-1: GIVEN I create the series 'Year 7 Swimming', weekly on Tuesday 10:00–12:00, Branch A → Aquatic Centre, 11 passengers, Term 1 2027 WHEN I save THEN an occurrence is created for every Tuesday school day in Term 1 2027 and each is allocated AC-2: GIVEN I leave the name, day, times, pickup, destination or date range empty WHEN I save THEN the series is not saved and the missing fields are highlighted AC-3: GIVEN the series has a contact person and phone WHEN occurrences are confirmed THEN the contact receives one summary SMS for the term, not one per occurrence | Must | 5 | Medium | FR-11 | Release 1 (MVP) | Draft
US-09 | EP-02 | Fixed & Recurring Trips | As a transport coordinator, I want to have recurring trips skip school holidays and public holidays automatically, so that vans aren't reserved on days when there's no school. | AC-1: GIVEN a Tuesday falls in the school holidays WHEN the series is generated THEN no occurrence is created for that Tuesday AC-2: GIVEN a Monday is a NZ public holiday WHEN a Monday series is generated THEN no occurrence is created for that Monday AC-3: GIVEN the administrator adds a teacher-only day after the series exists WHEN the calendar is saved THEN the occurrence on that day is cancelled, its van is released, and the series contact is notified | Must | 3 | Medium | FR-12 | Release 1 (MVP) | Draft
US-10 | EP-02 | Fixed & Recurring Trips | As a transport coordinator, I want to change or cancel a single occurrence without affecting the rest of the series, so that one-off changes such as a cancelled swimming session are easy. | AC-1: GIVEN the 'Year 7 Swimming' series has 10 occurrences WHEN I cancel the 14/05 occurrence only THEN only that occurrence is cancelled, its van is released and the other 9 are unchanged AC-2: GIVEN I change the time from 10:00 to 11:00 and choose 'this and all following' WHEN I save THEN that occurrence and all later ones move to 11:00 and are re-allocated; earlier ones are unchanged | Must | 3 | Medium | FR-13 | Release 1 (MVP) | Draft
US-11 | EP-02 | Fixed & Recurring Trips | As a transport coordinator, I want to have fixed trips allocated before ad-hoc requests, so that known commitments are always covered. | AC-1: GIVEN an ad-hoc request is Proposed on Van 1 on Tuesday 10:00 WHEN I create a fixed series that needs Van 1 at that time and no other van fits THEN the fixed occurrence takes Van 1 and the ad-hoc request is re-allocated or moved to 'Needs attention' AC-2: GIVEN the ad-hoc request was already Confirmed WHEN the fixed series is created THEN the Confirmed booking is not moved; the clash is shown to me to resolve | Must | 3 | Medium | FR-14 | Release 1 (MVP) | Draft
US-12 | EP-02 | Fixed & Recurring Trips | As a transport coordinator, I want to import a term's fixed trips from a spreadsheet, so that I can set up a whole term quickly. | AC-1: GIVEN I upload a file based on the download template WHEN the file is processed THEN I see a preview showing valid rows and rows with errors (with reasons) before anything is saved AC-2: GIVEN I confirm the import WHEN it completes THEN valid series are created and allocated exactly as if I had entered them manually | Could | 5 | Medium | FR-15 | Later | Draft
US-13 | EP-03 | Automatic Allocation | As a transport coordinator, I want to have each new request automatically planned onto a suitable van, so that I only need to check and approve. | AC-1: GIVEN a valid request is submitted and a feasible plan exists WHEN planning runs THEN within 5 seconds the request is 'Proposed' with the van, planned pickup time and route position shown AC-2: GIVEN a booking is cancelled WHEN planning re-runs THEN unconfirmed bookings may be re-planned, and Confirmed bookings stay within BRL-12 AC-3: GIVEN planning runs WHEN it finishes THEN the decision is written to the audit log as 'System – automatic planning' | Must | 8 | High | FR-16, FR-23 | Release 1 (MVP) | Draft
US-14 | EP-03 | Automatic Allocation | As a transport coordinator, I want to be sure the system never double-books a van and always allows travel, stop and turnaround time, so that trips don't run late or clash. | AC-1: GIVEN Van 1's last drop-off is at Branch A at 11:30, dwell is 5 min, and the map service gives 20 min Branch A → Branch B WHEN a request needs pickup at Branch B at 11:45 (exact) THEN Van 1 is not proposed (earliest arrival 11:55) AC-2: GIVEN a van's route has stops at 9:00 and 9:30 WHEN anyone tries to add a stop that makes the van be in two places at once THEN it is prevented and the conflict is described AC-3: GIVEN a route has 10 passengers on board between stops 2 and 3 in an 11-seat van WHEN a request would add 2 passengers boarding at stop 2 THEN that insertion is rejected (BRL-02) | Must | 5 | High | FR-17 | Release 1 (MVP) | Draft
US-15 | EP-03 | Automatic Allocation | As a transport coordinator, I want to have the plan that uses the least paid van time and empty driving chosen, so that the hired fleet is used efficiently. | AC-1: GIVEN Van 1 is already running Branch A → Branch C at 8:30 with 5 free seats and Van 2 is idle at the depot WHEN a request Branch A → Branch C, 3 passengers, 8:35 ±10 min arrives THEN the request is added to Van 1's run rather than sending Van 2 AC-2: GIVEN two plans have equal van time WHEN one uses an 8-seat van and the other a 12-seat van for 6 passengers THEN the 8-seat van is proposed AC-3: GIVEN the administrator changes optimisation weights WHEN the next planning runs THEN the new weights are used and the change is audit-logged | Must | 5 | High | FR-18 | Release 1 (MVP) | Draft
US-16 | EP-03 | Automatic Allocation | As a transport coordinator, I want to see in plain words why the system chose a van, so that I can trust or change its decision. | AC-1: GIVEN a request is Proposed WHEN I open it THEN I see a reason such as 'Van 2: added to the 8:25 Branch A run (shared); 7 of 8 seats used; Van 1 busy 9:00–11:30 (Swimming).' AC-2: GIVEN a request is 'Needs attention' WHEN I open it THEN I see which rule blocked each van, e.g. 'Van 1 – outside contracted hours' | Should | 3 | Medium | FR-19 | Release 2 | Draft
US-17 | EP-03 | Automatic Allocation | As a transport coordinator, I want to have requests that can't be allocated flagged with suggested alternatives, so that I can resolve them quickly. | AC-1: GIVEN no van is free at the requested time WHEN allocation runs THEN status is 'Needs attention' and I see up to 3 options, e.g. 'Van 1 free if departing 10:40' or 'Swap with unconfirmed PT-2026-0139' AC-2: GIVEN I pick a suggested option WHEN I confirm it THEN the booking is updated and the requester is notified of the change AC-3: GIVEN no alternative exists WHEN I open the request THEN I see 'No alternatives in ±60 min' and the conflicting bookings | Must | 5 | High | FR-20 | Release 1 (MVP) | Draft
US-19 | EP-03 | Automatic Allocation | As a transport coordinator, I want to have large groups split across several vans automatically, so that I don't have to create separate bookings. | AC-1: GIVEN vans have 12 and 8 passenger seats WHEN a request for 18 passengers is allocated THEN both vans are proposed on one booking, departing together AC-2: GIVEN not enough vans are free for the whole group WHEN allocation runs THEN the request goes to 'Needs attention' with the reason 'Group needs 2 vans; only 1 free' | Should | 5 | Medium | FR-22 | Release 2 | Draft
US-20 | EP-03 | Automatic Allocation | As a transport coordinator, I want to be sure a van that is unavailable or has expired compliance evidence is never used, so that we stay safe and legal. | AC-1: GIVEN Van 1's COF/WOF evidence expires on 02/03/2027 WHEN a request for 03/03/2027 is planned THEN Van 1 is excluded with the reason 'Compliance evidence expired' AC-2: GIVEN Van 2 is marked unavailable 10/03 08:00–12:00 WHEN a request overlaps that period THEN Van 2 is excluded AC-3: GIVEN a coordinator tries to assign an excluded van manually WHEN they save THEN the save is blocked with the reason | Must | 3 | Medium | FR-17, FR-40 | Release 1 (MVP) | Draft
US-22 | EP-04 | Coordinator Review & Scheduling | As a transport coordinator, I want to see a dashboard of requests awaiting my action, sorted by trip date and urgency, so that I handle the most pressing ones first. | AC-1: GIVEN there are 2 Needs-attention, 5 Proposed and 1 Urgent request WHEN I sign in THEN I see tiles 'Needs attention (2)', 'Awaiting approval (5)', 'Urgent (1)', 'Today's trips (n)', with Urgent items first AC-2: GIVEN I click a tile WHEN the list opens THEN it shows trip date/time, requester, route, passengers, proposed van and status, and can be filtered AC-3: GIVEN the other coordinator approves a request WHEN I am viewing the dashboard THEN the counts refresh within 30 seconds without reloading, so we don't act on the same item twice | Must | 5 | Medium | FR-25 | Release 1 (MVP) | Draft
US-23 | EP-04 | Coordinator Review & Scheduling | As a transport coordinator, I want to approve a proposed allocation in one click, or several at once, so that confirming is quick. | AC-1: GIVEN a request is Proposed WHEN I click 'Approve' THEN it becomes Confirmed and the requester receives the confirmation SMS within 1 minute AC-2: GIVEN I tick 6 Proposed requests WHEN I click 'Approve selected' THEN all 6 are Confirmed and 6 SMS are sent AC-3: GIVEN another coordinator already changed the request WHEN I click 'Approve' THEN I'm told it changed and shown the latest version before approving | Must | 3 | Low | FR-26 | Release 1 (MVP) | Draft
US-24 | EP-04 | Coordinator Review & Scheduling | As a transport coordinator, I want to change the van, time or stops of a booking with constraint warnings, so that I can make informed changes. | AC-1: GIVEN I move a booking to Van 1 at a time Van 1 cannot reach the pickup WHEN I try to save THEN saving is blocked and the reason is shown AC-2: GIVEN my change triggers only a soft warning (e.g. more van time than the proposal) WHEN I save THEN I must enter a reason, and the change is audit-logged AC-3: GIVEN I change a Confirmed booking's pickup time or van WHEN I save THEN the requester gets a 'Your trip has changed' SMS and the driver link shows 'Route updated' | Must | 5 | Medium | FR-23, FR-27 | Release 1 (MVP) | Draft
US-25 | EP-04 | Coordinator Review & Scheduling | As a transport coordinator, I want to decline a request with a reason, so that the requester knows why and can make other arrangements. | AC-1: GIVEN I click 'Decline' WHEN I choose a reason (No van available / Outside hours / Duplicate / Not a college trip / Other) and confirm THEN status becomes Declined and the requester receives the reason by SMS AC-2: GIVEN I choose 'Other' WHEN I try to confirm THEN a free-text reason is required | Must | 2 | Low | FR-28 | Release 1 (MVP) | Draft
US-26 | EP-04 | Coordinator Review & Scheduling | As a transport coordinator, I want to see day and week calendar views of all vans, so that I can see the whole schedule at a glance. | AC-1: GIVEN I open the day view WHEN it loads THEN each van is a row with bookings as blocks from 7:00 to 18:00, colour-coded by status, and fixed trips marked with a repeat icon AC-2: GIVEN I click a booking block WHEN it opens THEN I see its full details and can Approve/Change/Decline AC-3: GIVEN a new van is added by the administrator WHEN I open the calendar THEN the new van appears as a row with no other changes | Must | 5 | Medium | FR-29 | Release 1 (MVP) | Draft
US-27 | EP-04 | Coordinator Review & Scheduling | As a transport coordinator, I want to create a booking on behalf of someone who phoned or emailed, so that all trips are in one system. | AC-1: GIVEN I click 'New booking' WHEN I fill the same fields as the public form and choose source 'Phone' THEN the booking is created, allocated and shown with source 'Phone' AC-2: GIVEN I want to confirm straight away WHEN I tick 'Approve now' THEN it is Confirmed immediately if no clash, and the requester is notified | Must | 2 | Low | FR-30 | Release 1 (MVP) | Draft
US-28 | EP-04 | Coordinator Review & Scheduling | As a transport coordinator, I want to drag and drop a booking to another van or time on the calendar, so that changes are fast. | AC-1: GIVEN I drag a booking onto another van's row WHEN I drop it THEN the same clash checks as a manual change are applied before saving AC-2: GIVEN the drop would breach a hard constraint WHEN I drop it THEN the booking snaps back and the reason is shown | Could | 5 | Medium | FR-31 | Later | Draft
US-29 | EP-04 | Coordinator Review & Scheduling | As a transport coordinator, I want to print a daily stop-by-stop run sheet per van, so that the driver and I have a paper backup of the route. | AC-1: GIVEN I choose a date and van WHEN I click 'Run sheet' THEN an A4 printable/PDF sheet lists each stop in order: time, address, pick up/drop off, ref, contact & phone, passengers on/off, breaks AC-2: GIVEN there are no trips for that van and day WHEN I request the run sheet THEN it says 'No trips scheduled' | Should | 3 | Low | FR-32 | Release 2 | Draft
US-30 | EP-05 | Notifications & Requester Self-Service | As a requester, I want to receive an SMS when my request is received, confirmed, changed or declined, so that I know where things stand without calling. | AC-1: GIVEN I submit a request WHEN it is received THEN I get an SMS within 1 minute: 'Polymath Transport: request PT-2026-0142 received for Tue 12 Mar, 10:00. We'll confirm soon. View: <link>' AC-2: GIVEN a coordinator confirms my request and it is pooled WHEN it is Confirmed THEN the SMS gives the van, pickup place and planned pickup time, and says 'Shared van – other stops on the way' AC-3: GIVEN I also gave an email address WHEN any notification is sent THEN the same message is also emailed AC-4: GIVEN an SMS fails to send WHEN the SMS provider returns an error THEN the failure is shown on the booking for the coordinator | Must | 5 | Medium | FR-33, FR-35 | Release 1 (MVP) | Draft
US-31 | EP-05 | Notifications & Requester Self-Service | As a requester, I want to get a reminder the day before my trip, so that I'm ready on time. | AC-1: GIVEN my Confirmed trip is on Wednesday WHEN it is 3:00 pm on Tuesday THEN I receive a reminder SMS with time, pickup and van AC-2: GIVEN my trip is on Monday WHEN it is 3:00 pm on the Friday before THEN I receive the reminder | Should | 2 | Low | FR-34 | Release 2 | Draft
US-32 | EP-05 | Notifications & Requester Self-Service | As a requester, I want to check or cancel my booking using the link in my SMS, without logging in, so that I can free up the van if plans change. | AC-1: GIVEN I open the link in my SMS WHEN the page loads THEN I see my booking status and details only AC-2: GIVEN I tap 'Cancel this trip' and confirm WHEN the cancellation is saved THEN the status becomes Cancelled, the van is released, coordinators are alerted if the trip is within 24 h, and I get a cancellation SMS AC-3: GIVEN I tap 'Ask for a change' and describe it WHEN I send it THEN the request goes to a coordinator as 'Change requested'; the booking is unchanged until they act AC-4: GIVEN someone alters the link token WHEN they open it THEN they see 'Link not valid' and no booking data | Must | 5 | Medium | FR-35 | Release 1 (MVP) | Draft
US-33 | EP-05 | Notifications & Requester Self-Service | As a transport coordinator, I want to be alerted to urgent or same-day requests and late cancellations, so that I can act quickly. | AC-1: GIVEN a same-day request is submitted WHEN it is received THEN all coordinators get an in-app alert, plus SMS/email if enabled in their preferences AC-2: GIVEN a Confirmed trip is cancelled less than 24 h before departure WHEN the cancellation is saved THEN coordinators are alerted | Should | 3 | Low | FR-36 | Release 2 | Draft
US-35 | EP-06 | Fleet, Driver & Location Management | As a administrator, I want to add, edit and retire hired vans, including setting their seating capacity, so that the system grows with the fleet without IT changes. | AC-1: GIVEN I add 'Van 3', supplier 'ABC Hire', 11 passenger seats, wheelchair access, hours Mon–Fri 7:30–16:00, start/end at Branch A WHEN I save THEN Van 3 is available for planning within those hours and appears on the calendar and map AC-2: GIVEN Van 2 has 12 seats and I change it to 8 (seats removed for cargo) WHEN I save THEN future unconfirmed plans are re-checked, and Confirmed bookings with more than 8 passengers are listed for me to resolve AC-3: GIVEN I add a temporary van available 01/03–05/03 only WHEN planning runs for 06/03 THEN that van is not used AC-4: GIVEN I retire Van 1, which has future Confirmed bookings WHEN I try to save THEN I am warned and shown those bookings to reassign first | Must | 3 | Low | FR-38 | Release 1 (MVP) | Draft
US-36 | EP-06 | Fleet, Driver & Location Management | As a administrator, I want to save branches and venues and override travel times where the map is wrong, so that planning uses accurate local times. | AC-1: GIVEN I add 'Branch C' with its address WHEN I save THEN it appears under 'Our branches' on the form, and travel times are fetched from the map service AC-2: GIVEN coordinators know Branch A → Branch B really takes 25 min at 8:30 (map says 15) WHEN I enter a 25-min override THEN planning uses 25 min for that pair AC-3: GIVEN I deactivate a location WHEN I save THEN it disappears from the form but existing bookings keep it | Must | 3 | Low | FR-39 | Release 1 (MVP) | Draft
US-37 | EP-06 | Fleet, Driver & Location Management | As a transport coordinator, I want to mark a van unavailable and be reminded before its compliance evidence expires, so that hired vans are never booked when off-road or non-compliant. | AC-1: GIVEN Van 2's registration evidence expires in 14 days WHEN the daily check runs THEN coordinators get a reminder to request updated evidence from the supplier AC-2: GIVEN the supplier says Van 1 is off-road on Thursday and I mark it unavailable WHEN I save THEN unconfirmed bookings are re-planned; Confirmed bookings are listed for me to resolve | Must | 3 | Medium | FR-40 | Release 1 (MVP) | Draft
US-39 | EP-06 | Fleet, Driver & Location Management | As a administrator, I want to configure dwell, buffer and break times, flexibility, ride-time limits and other rules, so that the system matches how we work. | AC-1: GIVEN I change the return safety buffer from 15 to 20 minutes WHEN I save THEN new plans use 20 minutes, Confirmed bookings are unchanged, and the change is audit-logged AC-2: GIVEN I enter the 2027 term dates WHEN I save THEN fixed-trip series spanning 2027 are regenerated to match | Must | 3 | Low | FR-42, FR-12 | Release 1 (MVP) | Draft
US-40 | EP-07 | Reporting & Insights | As a member of college leadership, I want to see monthly reports of paid vs used van hours, route savings and unmet demand, so that we can manage the hire contract and decide whether to add vans. | AC-1: GIVEN I choose a month WHEN I open the utilisation report THEN I see per van: contracted hours, scheduled hours, idle paid hours, km, trips, passengers per run, % shared AC-2: GIVEN requests were declined or unfulfilled that month WHEN I open the demand report THEN I see how many, when, and why, grouped by purpose and branch, with 'extra hire van needed' shown separately | Should | 5 | Medium | FR-44, FR-45 | Release 2 | Draft
US-41 | EP-07 | Reporting & Insights | As a transport coordinator, I want to export bookings and reports to Excel/CSV, so that I can share or analyse the data. | AC-1: GIVEN I am viewing a filtered list or report WHEN I click 'Export' THEN a file downloads containing exactly the filtered rows and visible columns | Should | 2 | Low | FR-46 | Release 2 | Draft
US-42 | EP-07 | Reporting & Insights | As a business manager, I want to record the odometer reading for each trip, so that we can track kilometres per van for RUC and servicing. | AC-1: GIVEN a trip is Completed WHEN the driver/coordinator enters start and end odometer THEN the kilometres are calculated, and an end reading lower than the start is rejected | Could | 3 | Low | FR-47 | Later | Draft
US-43 | EP-08 | Security, Privacy & Audit | As a transport coordinator, I want to log in securely with two-factor authentication, so that only authorised staff can manage bookings. | AC-1: GIVEN I have a Coordinator account WHEN I sign in with password and 2FA code (or college SSO) THEN I reach the dashboard AC-2: GIVEN I am idle for 30 minutes WHEN I try to act THEN I must sign in again AC-3: GIVEN I have the Viewer role WHEN I open a booking THEN I cannot approve, change or decline it | Must | 3 | Medium | FR-43, FR-48, FR-51 | Release 1 (MVP) | Draft
US-44 | EP-08 | Security, Privacy & Audit | As a privacy officer, I want to have requesters see a short privacy notice, and old personal data removed automatically, so that we meet the NZ Privacy Act 2020. | AC-1: GIVEN I open the request form WHEN I look below the Send button THEN a short notice states what is collected, why, who sees it, how long it's kept and who to contact AC-2: GIVEN the retention period is 24 months WHEN a trip is more than 24 months old THEN the requester's name, phone and email are anonymised automatically, and trip statistics are kept | Must | 3 | Medium | FR-49 | Release 1 (MVP) | Draft
US-45 | EP-08 | Security, Privacy & Audit | As a transport coordinator, I want to have every change to a booking recorded (who, what, when, why), so that we can resolve questions and disputes. | AC-1: GIVEN any user or the system changes a booking WHEN the change is saved THEN the booking's history shows the timestamp, user/'System', fields before/after and reason AC-2: GIVEN I am an Administrator WHEN I try to edit or delete history THEN no such option exists | Must | 3 | Medium | FR-50 | Release 1 (MVP) | Draft
US-46 | EP-09 | Multi-stop Route Optimisation & Maps | As a requester, I want to add extra stops to my trip (e.g. pick up more people at another branch), so that one van run covers my whole journey. | AC-1: GIVEN I am on the form WHEN I tap '+ Add a stop' THEN a stop row appears with address, 'Pick up / Drop off' and passengers on/off; up to 3 extra stops AC-2: GIVEN I add a stop WHEN the request is planned THEN the stops are visited in the order I entered them AC-3: GIVEN passengers on board would go below 0 or above 99 at any stop WHEN I submit THEN I see a plain-language error on that stop | Should | 3 | Medium | FR-54 | Release 2 | Draft
US-47 | EP-09 | Multi-stop Route Optimisation & Maps | As a requester, I want to say how flexible my pickup time is and when I must arrive, so that my trip can share a van, but I still arrive on time. | AC-1: GIVEN I choose '±20 min' flexibility for a 9:00 pickup WHEN the request is planned THEN any planned pickup time between 8:40 and 9:20 is allowed AC-2: GIVEN I enter 'Must arrive by 9:30' WHEN the request is planned THEN no plan arriving after 9:30 is proposed AC-3: GIVEN I don't change flexibility WHEN I submit THEN the default of ±10 min is used | Should | 2 | Low | FR-55 | Release 2 | Draft
US-48 | EP-09 | Multi-stop Route Optimisation & Maps | As a transport coordinator, I want to have new requests combined into shared multi-stop routes automatically, so that fewer van runs carry the same people. | AC-1: GIVEN Van 2 has a run Branch A 8:25 → Branch C 8:55 with 3 passengers (8-seat van) WHEN a request Branch B → Sports Centre, 4 passengers, 8:45 ±10 arrives, and the detour is within limits THEN it is proposed as Branch A 8:25 → Branch B 8:40 → Branch C 8:55 → Sports Centre 9:10 on Van 2, marked 'Shared' AC-2: GIVEN adding a request would make an existing passenger's ride exceed direct time + the allowed extra time WHEN planning runs THEN that insertion is rejected (BRL-11) AC-3: GIVEN pooling adds 4 min to a Confirmed passenger's pickup WHEN the plan is proposed THEN it requires coordinator approval, and that requester is notified after approval (BRL-12) | Must | 8 | High | FR-56 | Release 1 (MVP) | Draft
US-49 | EP-09 | Multi-stop Route Optimisation & Maps | As a transport coordinator, I want to optimise a whole day's routes and see the savings before accepting, so that the day's plan is as efficient as possible without surprises. | AC-1: GIVEN tomorrow has 14 bookings on 2 vans WHEN I click 'Optimise day' THEN within 60 seconds I see before/after: van runs, paid hours, km, and the list of bookings whose times would change AC-2: GIVEN I untick 2 of the proposed changes WHEN I click 'Accept selected' THEN only the ticked changes are applied, and affected requesters and drivers are notified AC-3: GIVEN it is 2:00 pm on the previous school day WHEN the automatic run completes THEN coordinators get an alert 'Optimisation ready – saves X h' and nothing changes until accepted | Must | 8 | High | FR-57 | Release 1 (MVP) | Draft
US-50 | EP-09 | Multi-stop Route Optimisation & Maps | As a transport coordinator, I want to see each van's route for the day on a map, so that I can check that the plan makes sense at a glance. | AC-1: GIVEN I open the route map for 12/03 and choose Van 1 WHEN it loads THEN I see numbered stops joined in order, with planned times and passengers on board, and gap jobs highlighted AC-2: GIVEN I click a stop WHEN it opens THEN I see its booking(s) and can open them | Should | 5 | Medium | FR-59 | Release 2 | Draft
US-51 | EP-09 | Multi-stop Route Optimisation & Maps | As a transport coordinator, I want to reorder stops or move a booking to another van's route, so that I can apply local knowledge the system doesn't have. | AC-1: GIVEN I drag stop 3 before stop 2 WHEN I save THEN times are recalculated and saved if all constraints hold AC-2: GIVEN my change makes a pickup miss its time window WHEN I try to save THEN I see which booking is affected, and saving requires a reason (or is blocked for hard constraints) | Should | 5 | Medium | FR-60 | Release 2 | Draft
US-52 | EP-05 | Notifications & Requester Self-Service | As a hire driver, I want to open today's stop-by-stop route from a link on my phone, so that I know exactly where to go, who to collect and whom to call. | AC-1: GIVEN my van has Confirmed stops tomorrow WHEN it is 4:00 pm today THEN I receive an SMS with a secure link to tomorrow's route AC-2: GIVEN I open the link WHEN the page loads THEN I see stops in order with time, address, pick up/drop off, contact name & phone, passengers, breaks, and a 'Navigate' button AC-3: GIVEN a coordinator changes a Confirmed stop on my route today WHEN the change is saved THEN I receive 'Route updated' by SMS and the link shows the new route AC-4: GIVEN the link is older than the end of that day or has been altered WHEN it is opened THEN no booking data is shown | Must | 3 | Medium | FR-61 | Release 1 (MVP) | Draft
US-53 | EP-09 | Multi-stop Route Optimisation & Maps | As a transport coordinator, I want to have addresses located and travel times calculated automatically by a map service, so that planning works for any errand address without me entering travel times. | AC-1: GIVEN a request uses an address that isn't saved WHEN it is submitted THEN the address is located and travel times to other stops are fetched and cached AC-2: GIVEN the map service is unavailable WHEN planning runs THEN cached/default times are used and the proposal is flagged 'Estimated travel time' AC-3: GIVEN an override exists for a location pair WHEN planning runs THEN the override is used instead of the map time | Must | 5 | Medium | FR-52, FR-53 | Release 1 (MVP) | Draft
US-54 | EP-09 | Multi-stop Route Optimisation & Maps | As a transport coordinator, I want to use a van that is waiting for a return trip for other jobs in between, when they can finish in time, so that paid waiting time isn't wasted. | AC-1: GIVEN Van 1 drops a swimming group at the Aquatic Centre at 9:30 with return pickup at 11:30 and a 15-min safety buffer WHEN a staff errand Branch B → supplier → Branch B, planned to finish so the van is back at the Aquatic Centre by 11:15, is requested THEN it is proposed on Van 1 as a gap job AC-2: GIVEN the errand would get the van back to the Aquatic Centre at 11:20 (inside the buffer) WHEN planning runs THEN Van 1 is not used for it AC-3: GIVEN the swimming booking has 'Van must stay with us' ticked WHEN planning runs THEN no gap jobs are scheduled for Van 1 between 9:30 and 11:30 | Must | 5 | High | FR-58 | Release 1 (MVP) | Draft
US-55 | EP-03 | Automatic Allocation | As a transport coordinator, I want to have plans respect each hired van's contracted hours and the driver's breaks, so that we stay within the hire contract and drivers take legal breaks. | AC-1: GIVEN Van 2's contracted hours are 7:30–16:00 WHEN a request needs the van until 16:30 THEN Van 2 is not proposed, and the reason says 'Outside contracted hours' AC-2: GIVEN a route would give the driver 5.5 hours of work without a break WHEN planning runs THEN a 30-min break is inserted at a suitable stop, or the plan is rejected | Must | 3 | Medium | FR-62 | Release 1 (MVP) | Draft
US-56 | EP-06 | Fleet, Driver & Location Management | As a administrator, I want to record the hire supplier and each van's assigned driver, so that coordinators and requesters know who is driving and how to contact them. | AC-1: GIVEN I record supplier 'ABC Hire' with contact, contract ref and charging model 'per hour' WHEN I save THEN the supplier can be selected on vans, and its charging model is shown on reports AC-2: GIVEN the supplier changes Van 1's driver from 12/03 WHEN I enter the new driver name and phone from 12/03 THEN run sheets and driver links from 12/03 use the new driver; earlier dates are unchanged | Must | 2 | Low | FR-63 | Release 1 (MVP) | Draft
US-57 | EP-09 | Multi-stop Route Optimisation & Maps | As a transport coordinator, I want to record that a van is running late and see who is affected, so that I can warn people before they wait too long. | AC-1: GIVEN Van 1 is 15 min late WHEN I record '+15 min' from the current stop THEN later stop times are recalculated and missed time windows are highlighted AC-2: GIVEN affected bookings are shown WHEN I click 'Notify affected' THEN each requester gets an SMS with the new estimated time | Could | 3 | Medium | FR-64 | Later | Draft

## Requirements
Req ID | Type | Title | Description | Priority | Objective | BR ref | Stories | Source
BR-01 | Business | Single, simple request channel | Staff shall be able to request transport through one public online form, with no account or login. Name and phone number are mandatory. | Must | BO-04 |  |  | Problem statement
BR-02 | Business | Recurring fixed trips | The college shall be able to schedule known recurring trips (e.g. swimming, basketball, badminton) in advance for whole terms. | Must | BO-01 |  |  | Problem statement
BR-03 | Business | Automatic allocation | The system shall automatically propose the most efficient allocation of vans (and drivers, where applicable) for every trip. | Must | BO-01, BO-03 |  |  | Problem statement
BR-04 | Business | Coordinator control | Transport coordinators shall approve, change or decline every allocation before it is confirmed to the requester. | Must | BO-01, BO-02 |  |  | Problem statement
BR-05 | Business | Safe, clash-free scheduling | The solution shall prevent double bookings, keep each hired van within its contracted hours with legal driver breaks, and prevent use of vans that are unavailable or lack current compliance evidence. | Must | BO-02 |  |  | BA analysis (H&S); answer 1
BR-06 | Business | Keep requesters informed | Requesters shall be told the status of their request and any changes without having to contact a coordinator. | Must | BO-05 |  |  | BA analysis
BR-07 | Business | Scalable through configuration | College staff shall be able to add or change hired vans (including seating capacity), locations, term dates and rules without software changes. | Must | BO-06 |  |  | Problem statement; answer 3
BR-08 | Business | Usage and demand insight | The college shall have reports on van usage and on unmet demand to support fleet decisions. | Should | BO-03 |  |  | BA analysis
BR-09 | Business | Usable by non-technical staff | The solution shall be easy to use on phones and computers by staff with low technical confidence. | Must | BO-04 |  |  | Problem statement
BR-10 | Business | Privacy and access control | Personal information shall be handled in line with the NZ Privacy Act 2020, and management functions shall be limited to authorised staff. | Must | — |  |  | Regulatory scan
BR-11 | Business | Accountability | All allocation decisions and changes shall be recorded (who, what, when, why). | Must | BO-02 |  |  | BA analysis
BR-12 | Business | Multi-stop route optimisation | The system shall combine trips into efficient multi-stop routes and use a van's waiting time between legs for other jobs, while meeting every requester's time window and ride-time limits. | Must | BO-07, BO-03 |  |  | Stakeholder answers 4 & 5
FR-01 | Functional | Public request form | The system shall provide a public, no-login, mobile-responsive request form reachable by URL and printable QR code. | Must |  | BR-01, BR-09 | US-01 | BA analysis
FR-02 | Functional | Mandatory & optional fields | Mandatory: requester name, phone, trip date, trip purpose (one tap: Class trip / Sport / Staff errand / Meeting or event / Other), pickup time, pickup location, destination, number of passengers, and 'Return trip needed?' (plus return pickup time if yes). Optional: email, extra stops, time flexibility, 'Must arrive by', 'Van must stay with us', special requirements, department, notes. | Must |  | BR-01 | US-01, US-02, US-03 | BA analysis
FR-03 | Functional | Field validation | The system shall validate NZ phone numbers (mobile and landline; stored in +64 format), reject past dates, require return time after departure, limit passengers to 1–99, and show plain-language error messages next to the field. | Must |  | BR-01, BR-09 | US-01 | BA analysis
FR-04 | Functional | Submission confirmation | On submit the system shall generate a unique reference (format PT-YYYY-NNNN), show a confirmation screen with a summary, trigger allocation (FR-16) and send an acknowledgement (FR-33). | Must |  | BR-01, BR-06 | US-01 | BA analysis
FR-05 | Functional | Location selection | Pickup, destination and stops shall be chosen from a list (Branches first, then Venues) or entered as any address, with address autocomplete (FR-52). | Must |  | BR-01, BR-07 | US-02 | BA analysis
FR-06 | Functional | Return trip | The form shall ask 'Do you need a return trip?' If yes, it asks for the return pickup time and offers the tick-box 'Van must stay with us (e.g. equipment or safety)'. Otherwise the van may do other jobs between legs (BRL-06). | Must |  | BR-03, BR-12 | US-03 | BA analysis
FR-07 | Functional | Short-notice & out-of-hours warning | The form shall warn the requester when the trip is within the minimum notice period or outside operating hours; the request is still accepted and flagged (BRL-13). | Should |  | BR-06 | US-05 | BA analysis
FR-08 | Functional | Anti-abuse protection | The form shall use an invisible CAPTCHA/honeypot and rate limits (default 5 submissions per phone and per IP per hour), and flag first-time phone numbers (BRL-15). | Must |  | BR-10 | US-06 | BA analysis
FR-09 | Functional | Special requirements | The form shall offer tick-boxes for wheelchair access and large equipment, plus a free-text 'Anything else we should know?'. | Should |  | BR-03 | US-04 | BA analysis
FR-10 | Functional | Availability hint | After the date is chosen, the form may show a simple 'busy/free' indication by time of day, without showing other requesters' details. | Could |  | BR-01 | US-07 | BA analysis
FR-11 | Functional | Recurring series | Coordinators shall create a fixed-trip series: name, activity, contact person & phone, weekly/fortnightly pattern and day(s), times, stops, passengers, return trip / 'van must stay', preferred van (optional), and date range or term(s). | Must |  | BR-02 | US-08 | BA analysis
FR-12 | Functional | Term & holiday calendar | The system shall hold term dates, NZ public holidays and college non-school days, and shall not generate occurrences on those days (BRL-14). | Must |  | BR-02 | US-09 | BA analysis
FR-13 | Functional | Occurrence exceptions | Coordinators shall be able to change or cancel one occurrence, or 'this and all following', without affecting other occurrences; the series contact is notified. | Must |  | BR-02, BR-06 | US-10 | BA analysis
FR-14 | Functional | Fixed-trip priority | Fixed-trip occurrences shall be allocated before ad-hoc requests (BRL-07) when the series is created and whenever the calendar changes. | Must |  | BR-02, BR-03 | US-11 | BA analysis
FR-15 | Functional | Bulk import | Coordinators may import fixed-trip series from an Excel/CSV template, with a validation report before saving. | Could |  | BR-02 | US-12 | BA analysis
FR-16 | Functional | Automatic allocation trigger | The system shall run allocation automatically on every new or changed request and every cancellation, and on demand. Result: 'Proposed' or 'Needs attention' within 5 seconds. | Must |  | BR-03 | US-13 | BA analysis
FR-17 | Functional | Hard constraints | Allocation and routing shall enforce BRL-01 to BRL-06, BRL-16 and BRL-17 without exception. | Must |  | BR-03, BR-05 | US-14, US-20 | BA analysis
FR-18 | Functional | Preference ranking | Allocation shall rank feasible options using BRL-08, with administrator-editable weights. | Must |  | BR-03 | US-15 | BA analysis
FR-19 | Functional | Allocation explanation | Each proposal shall show a plain-English reason, e.g. 'Van 2: added to the 8:25 run from Branch A (shared with PT-2026-0140); +6 min for the other passengers; saves a separate 35-min trip.' | Should |  | BR-04, BR-11 | US-16 | BA analysis
FR-20 | Functional | No-fit handling | When no allocation is possible the system shall apply BRL-10 and show the alternatives to the coordinator. | Must |  | BR-03, BR-04 | US-17 | BA analysis
FR-22 | Functional | Multi-van split | The system shall propose multi-van allocations for groups larger than one van (BRL-09). | Should |  | BR-03 | US-19 | BA analysis
FR-23 | Functional | Confirmed bookings locked | The system shall never change a Confirmed booking automatically; it may only suggest changes to a coordinator. | Must |  | BR-04 | US-13, US-24 | BA analysis
FR-25 | Functional | Coordinator dashboard | The dashboard shall show counts and lists of: Needs attention, Proposed (awaiting approval), Urgent, and Today's trips, sorted by trip date and urgency, with filters by status, van, date and location. | Must |  | BR-04 | US-22 | BA analysis
FR-26 | Functional | Approve | Coordinators shall approve single or multiple proposals in one action; status becomes Confirmed and the requester is notified. | Must |  | BR-04, BR-06 | US-23 | BA analysis
FR-27 | Functional | Change booking | Coordinators shall change van, times, stops or passengers with a live constraint check, and see the recalculated route. A reason is required to save over a warning; hard-constraint breaches cannot be saved. | Must |  | BR-04, BR-05 | US-24 | BA analysis
FR-28 | Functional | Decline | Coordinators shall decline a request with a reason (pick-list plus optional text); the requester is notified. | Must |  | BR-04, BR-06 | US-25 | BA analysis
FR-29 | Functional | Calendar views | Day view (timeline per van), week view and list view, colour-coded by status, with fixed trips visually distinct. | Must |  | BR-04 | US-26 | BA analysis
FR-30 | Functional | Booking on behalf | Coordinators shall create a booking for someone who phoned or emailed, recording the source (Phone/Email/In person). | Must |  | BR-01, BR-04 | US-27 | BA analysis
FR-31 | Functional | Drag and drop | Coordinators may drag a booking to another van or time on the calendar, with the same validation as FR-27. | Could |  | BR-04 | US-28 | BA analysis
FR-32 | Functional | Daily run sheet | Printable/PDF run sheet per van for a chosen day, listing stops in order: time, address, pick up / drop off, booking ref, contact name & phone, passengers on/off, notes. | Should |  | BR-04 | US-29 | BA analysis
FR-33 | Functional | Status notifications | The system shall send SMS (and email if provided) when a request is received, confirmed, changed, declined or cancelled. Confirmations state the pickup time and place and whether the van is shared. Templates can be edited by the administrator. | Must |  | BR-06 | US-30 | BA analysis
FR-34 | Functional | Trip reminder | The system shall send a reminder at a configurable time on the previous school day (default 3:00 pm; Friday for Monday trips). | Should |  | BR-06 | US-31 | BA analysis
FR-35 | Functional | Secure self-service link | Each notification shall include a unique, unguessable link that lets the requester view status and cancel, or ask for a change (which goes to a coordinator), with no login. | Must |  | BR-06, BR-10 | US-32 | BA analysis
FR-36 | Functional | Coordinator alerts | Coordinators shall be alerted (in-app, plus email/SMS configurable) about urgent or same-day requests, Needs-attention items, and cancellations within 24 h of the trip. | Should |  | BR-04 | US-33 | BA analysis
FR-38 | Functional | Hired van register | Administrators shall add, edit and retire vans: name, registration, hire supplier, passenger seating capacity (editable), features, start/end location, contracted hours per weekday, available date range (for temporary extra hires), status (Active/Unavailable/Retired), and compliance evidence dates (COF/WOF, registration). There is no limit on the number of vans. | Must |  | BR-07, BR-05 | US-35 | BA analysis
FR-39 | Functional | Locations & travel-time overrides | Administrators shall maintain saved locations (name, type: Branch/Venue/Other, address, active flag) and optional travel-time overrides for specific location pairs (BRL-20). | Must |  | BR-07 | US-36 | BA analysis
FR-40 | Functional | Unavailability & compliance evidence | Coordinators shall mark a van unavailable for a period (e.g. off-road, supplier notice). The system shall remind them before compliance evidence expires (default 14 days) so they can request updated evidence from the supplier, and exclude the van from the expiry date. | Must |  | BR-05 | US-37, US-20 | BA analysis
FR-42 | Functional | Settings | Administrators shall configure dwell, buffer and break times, default flexibility, extra ride-time limit, minimum notice, operating hours, reminder and auto-optimise times, rate limits, manual-review triggers, optimisation weights and data retention period. | Must |  | BR-07 | US-39 | BA analysis
FR-43 | Functional | User management | Administrators shall create and deactivate staff accounts with the roles Coordinator, Administrator or Viewer. | Must |  | BR-10 | US-43 | BA analysis
FR-44 | Functional | Utilisation & efficiency report | Per van and period: contracted (paid) hours, scheduled hours, idle paid hours, driving vs waiting time, km, trips, passengers per van run, % of bookings shared, and estimated van hours saved by pooling and gap-filling. | Should |  | BR-08, BR-12 | US-40 | BA analysis
FR-45 | Functional | Demand & unmet-demand report | Requests by purpose, branch/destination, department and source; declined or unfulfilled requests with reasons ('extra hire van needed' shown separately). | Should |  | BR-08 | US-40 | BA analysis
FR-46 | Functional | Export | Any list or report can be exported to Excel/CSV. | Should |  | BR-08 | US-41 | BA analysis
FR-47 | Functional | Odometer capture | Start/end odometer may be recorded per trip to calculate kilometres per van (supports RUC and servicing). | Could |  | BR-08 | US-42 | BA analysis
FR-48 | Functional | Staff authentication | Staff users shall sign in with two-factor authentication (or college single sign-on if available); sessions time out after 30 minutes idle. | Must |  | BR-10 | US-43 | BA analysis
FR-49 | Functional | Privacy notice & retention | The form shall show a short privacy notice. Requester personal details shall be anonymised automatically after the retention period (default 24 months after the trip). | Must |  | BR-10 | US-44 | BA analysis
FR-50 | Functional | Audit trail | The system shall log every create, change, approve, decline, cancel and automatic allocation (user/system, timestamp, before/after, reason). The log is read-only. | Must |  | BR-11 | US-45 | BA analysis
FR-51 | Functional | Role-based access | The public can only submit requests and see their own booking via its secure link; Viewers see calendars and reports; Coordinators manage bookings; Administrators also manage settings and users. | Must |  | BR-10 | US-43 | BA analysis
FR-52 | Functional | Address lookup | The system shall locate (geocode) any address through a map service, with autocomplete on the form. Addresses that cannot be located reliably are flagged (BRL-15). | Must |  | BR-01, BR-12 | US-53 | BA analysis
FR-53 | Functional | Travel-time calculation | The system shall get travel times and distances between stops from the map service (for the time of day where available), cache them, and apply overrides and fallbacks (BRL-20). | Must |  | BR-12 | US-53 | BA analysis
FR-54 | Functional | Extra stops on a request | Requesters shall be able to add up to 3 extra stops (pick up or drop off, with passengers on/off) using '+ Add a stop'. | Should |  | BR-01, BR-12 | US-46 | BA analysis
FR-55 | Functional | Time flexibility | The form shall offer 'How flexible is your pickup time?' (Exact / ±10 / ±20 / ±30 min; default ±10) and an optional 'Must arrive by'. | Should |  | BR-12 | US-47 | BA analysis
FR-56 | Functional | Route insertion & pooling | For each new or changed request, the system shall evaluate inserting its stops into every van's route for that day and choose the lowest-cost feasible plan, pooling with other bookings where BRL-11 allows. | Must |  | BR-03, BR-12 | US-48 | BA analysis
FR-57 | Functional | Optimise day | Coordinators shall run 'Optimise day' on demand, and it also runs automatically (BRL-19). It shows a before/after comparison (vans used, paid hours, km, affected Confirmed bookings) and lets the coordinator accept all, some or none of the changes. | Must |  | BR-04, BR-12 | US-49 | BA analysis
FR-58 | Functional | Gap-filling between legs | For return trips, the system shall schedule other jobs in the gap between the outbound drop-off and the return pickup when BRL-06 allows, and label them as gap jobs on the route. | Must |  | BR-12 | US-54 | BA analysis
FR-59 | Functional | Route map | Coordinators shall see each van's route for a day on a map, with numbered stops, planned times, passengers on board and gap jobs. | Should |  | BR-04, BR-12 | US-50 | BA analysis
FR-60 | Functional | Manual route editing | Coordinators shall reorder stops or move a booking to another van's route. The system recalculates times and checks all constraints before saving (same rules as FR-27). | Should |  | BR-04 | US-51 | BA analysis
FR-61 | Functional | Driver route link | The system shall send each van's driver (and supplier contact) a secure, no-login link to the day's stop-by-stop route, with contact names/phones and a navigation link per stop. An SMS 'Route updated' is sent when confirmed stops change. | Must |  | BR-06, BR-10 | US-52 | BA analysis
FR-62 | Functional | Contracted hours & breaks | Routing shall keep each van within its contracted hours and insert driver breaks (BRL-05), showing breaks on the route and run sheet. | Must |  | BR-05 | US-55 | BA analysis
FR-63 | Functional | Supplier & driver details | Administrators shall record hire suppliers (name, contact, contract reference, charging model) and, per van and date, the assigned driver's name and phone (copied forward until changed). | Must |  | BR-05, BR-07 | US-56 | BA analysis
FR-64 | Functional | Record delays | Coordinators may record that a van is running late by N minutes. The system recalculates later stop times, flags missed time windows, and offers an SMS to affected requesters. | Could |  | BR-06 | US-57 | BA analysis
NFR-01 | Non-functional – Usability | Usability | A first-time requester can complete the form without help. [Measure: In a test with 5 staff, 5 of 5 complete it unaided; median 2 minutes or less] | Must |  |  |  | BA analysis
NFR-02 | Non-functional – Usability | Usability | Plain language throughout; no technical jargon; one question per field; the form fits on one scrolling page. [Measure: Reviewed against NZ plain-language guidance; at most 12 visible fields by default] | Must |  |  |  | BA analysis
NFR-03 | Non-functional – Accessibility | Accessibility | Conforms to WCAG 2.2 Level AA (contrast, keyboard use, screen-reader labels, large touch targets). [Measure: Accessibility audit before go-live] | Must |  |  |  | BA analysis
NFR-04 | Non-functional – Compatibility | Compatibility | Works on phones (360 px wide and up), tablets and desktops; latest 2 versions of Chrome, Safari, Edge and Firefox; iOS and Android. [Measure: Cross-device test pass] | Must |  |  |  | BA analysis
NFR-05 | Non-functional – Performance | Performance | Pages load in 3 seconds or less on 4G; a single request is planned in 5 seconds or less; 'Optimise day' finishes in 60 seconds or less. [Measure: Measured at 20 vans / 200 stops per day] | Must |  |  |  | BA analysis
NFR-06 | Non-functional – Availability | Availability | 99.5% availability 06:30–19:00 Mon–Fri (NZ time); maintenance outside these hours. [Measure: Monthly uptime report] | Should |  |  |  | BA analysis
NFR-07 | Non-functional – Scalability | Scalability | Supports at least 20 vans, 50 locations, 20 staff users and 5 years of history with no code change. [Measure: Load/volume test] | Must |  |  |  | BA analysis
NFR-08 | Non-functional – Security | Security | HTTPS (TLS 1.2+), encryption at rest, OWASP Top 10 controls, 2FA for staff, secure unguessable self-service tokens. [Measure: Security review / penetration test before go-live] | Must |  |  |  | BA analysis
NFR-09 | Non-functional – Privacy | Privacy | Complies with NZ Privacy Act 2020 (collection limited to what is needed, notice, security, access/correction, retention, breach notification). [Measure: Privacy Officer sign-off; privacy impact assessment] | Must |  |  |  | BA analysis
NFR-10 | Non-functional – Data residency | Data residency | Data hosted in New Zealand or Australia unless the college agrees otherwise. [Measure: Hosting contract (confirm – Q-13)] | Should |  |  |  | BA analysis
NFR-11 | Non-functional – Resilience | Resilience | Daily backups; RPO 24 h; RTO 1 school day; restore tested each term. [Measure: Restore test record] | Must |  |  |  | BA analysis
NFR-12 | Non-functional – Localisation | Localisation | NZ time zone including daylight saving; dates DD/MM/YYYY; times shown as '10:30 am'; NZ English. [Measure: Test cases across DST changeover] | Must |  |  |  | BA analysis
NFR-13 | Non-functional – Maintainability | Maintainability | Vans, drivers, locations, travel times, term dates, templates and rules are changed through admin screens, with no developer needed. [Measure: Admin walkthrough (BO-06)] | Must |  |  |  | BA analysis
NFR-14 | Non-functional – Supportability | Supportability | Context help on each screen; one-page quick guide for requesters; coordinator training of 1 hour or less. [Measure: Training feedback] | Should |  |  |  | BA analysis
NFR-15 | Non-functional – Auditability | Auditability | Audit records cannot be edited or deleted by any user role and are kept for at least the data retention period. [Measure: Security test] | Must |  |  |  | BA analysis
NFR-16 | Non-functional – Optimisation quality | Optimisation quality | On a replay of 4 weeks of real requests, the optimised plan uses fewer paid van hours than the coordinators' manual plan. [Measure: Target: 15% or more saving (confirm after baseline)] | Should |  |  |  | BA analysis
NFR-17 | Non-functional – Resilience (map service) | Resilience (map service) | If the map/routing service is unavailable, booking and approval still work using cached/default travel times, with proposals flagged. [Measure: Failover test] | Must |  |  |  | BA analysis

## Business Rules
Rule ID | Type | Rule | Default / configurable
BRL-01 | Hard constraint | A van can only be in one place at a time. Every route is timed from its start location using travel time between consecutive stops, dwell time at each stop (BRL-16), and a turnaround buffer after the last drop-off of a run. | Dwell 5 min; turnaround 10 min
BRL-02 | Hard constraint | At every point on a route, the number of passengers on board must not exceed the van's configured passenger seating capacity (excluding the driver). | Capacity set per van
BRL-03 | Hard constraint | The van must be 'Active', inside its available date range (for temporary hires), not blocked (off-road/unavailable), and have current compliance evidence (COF/WOF, registration) on record for the trip date. | —
BRL-04 | Hard constraint | The van must have every feature the trip needs (e.g. wheelchair access, tow bar, large luggage space). | —
BRL-05 | Hard constraint | Each van's route must fit within its contracted hours for that day (start/end location and times), and include driver rest breaks. The NZ work-time rules require a 30-minute break after at most 5.5 hours of work time; the supplier remains responsible for compliance. | Hours per van; break 30 min after 5.5 h (confirm with supplier)
BRL-06 | Return trips & gap-filling | For a return trip, the van is released after the outbound drop-off and must be back at the return pickup on time. Another job may be done in between only if its planned finish + travel to the return pickup + safety buffer is no later than the return pickup time. If the requester ticked 'Van must stay with us', the van waits. | Safety buffer 15 min
BRL-07 | Priority | Allocation order: (1) Confirmed bookings are never moved; (2) fixed-trip occurrences; (3) ad-hoc requests in order of trip date, then submission time; (4) a coordinator may set a request to 'High priority'. | —
BRL-08 | Optimisation goal (soft) | Among feasible plans, prefer in this order: (a) fewest vans and least paid van time; (b) least total travel time/distance (empty running); (c) smallest deviation from preferred times; (d) smallest van that fits; (e) balanced use across vans. | Weights editable by the administrator (depends on the hire charging model – Q-15)
BRL-09 | Split | If passengers exceed the largest single van, propose the fewest vans that together fit the group, all departing together. | —
BRL-10 | No fit | If no feasible plan exists, set status 'Needs attention', list the conflicts, and suggest up to 3 alternatives: nearest feasible time within the search window, a split across vans, a swap involving unconfirmed bookings only, or 'extra hire van needed'. | Search window ±60 min
BRL-11 | Pooling (shared rides) | Requests may share a van when each passenger's time in the van is no more than their direct travel time + the allowed extra ride time, each pickup falls inside the requester's time window, and capacity allows. Pooled bookings are marked 'Shared' and the requester is told. | Extra ride time: greater of 15 min or 50% of direct time
BRL-12 | Re-optimisation | When a booking is added, cancelled or changed, re-plan routes for unconfirmed bookings. A Confirmed booking's pickup time may only move within ±5 min, and only with coordinator approval; the requester is notified of any change. | Confirmed tolerance ±5 min
BRL-13 | Notice & hours | Requests with less than the minimum notice, or outside operating hours, are accepted but flagged 'Urgent' / 'Out of hours' for the coordinator. | 24 h notice; Mon–Fri 07:00–18:00
BRL-14 | Calendar | Fixed-trip occurrences are not generated on school holidays, NZ public holidays or college non-school days (e.g. teacher-only days). | Term calendar maintained by admin
BRL-15 | Manual review triggers | Requests are always set to 'Needs attention' when an address cannot be located reliably, wheelchair access is needed, or the phone number has never been seen before, even if a route is found. | Each trigger can be switched on/off
BRL-16 | Timing | Each stop has a dwell time for loading/unloading; stops flagged 'large equipment' or 'wheelchair' get the longer dwell time. | 5 min; 10 min for equipment/wheelchair
BRL-17 | Time windows | Pickup window = preferred time ± the requester's flexibility. If 'Must arrive by' is given, it is a hard deadline. Fixed-trip times have zero flexibility unless set on the series. | Default flexibility ±10 min
BRL-18 | Multi-stop requests | A single request may have up to N extra stops in the requester's order. Its stops stay in that order, and the passenger count may change at each stop. | N = 3
BRL-19 | Day optimisation | 'Optimise day' re-plans every route for a date. It may re-sequence stops and move unconfirmed bookings freely, but must respect BRL-12 for Confirmed bookings. The result is only a proposal until a coordinator accepts it. | Auto-run 2:00 pm the previous school day
BRL-20 | Travel times | Travel times come from the map service, for the planned time of day where available. An administrator override for a location pair always takes precedence. If the map service is unavailable, cached or default times are used and the proposal is flagged. | Default 30 min

## RTM
Req ID | Title | Type | Priority | Objective | BR ref | Epic | User stories | Test case IDs | Test status | Delivery status | Release | Regulatory link | Notes
FR-01 | Public request form | Functional | Must | BO-04 | BR-01, BR-09 | EP-01 | US-01 | TC-US-01-1, TC-US-01-2, TC-US-01-3, TC-US-01-4, TC-US-01-5 | Not started | Backlog | Release 1 (MVP)
FR-02 | Mandatory & optional fields | Functional | Must | BO-04 | BR-01 | EP-01 | US-01, US-02, US-03 | TC-US-01-1, TC-US-01-2, TC-US-01-3, TC-US-01-4, TC-US-01-5, TC-US-02-1, TC-US-02-2, TC-US-02-3, TC-US-03-1, TC-US-03-2, TC-US-03-3, TC-US-03-4 | Not started | Backlog | Release 1 (MVP)
FR-03 | Field validation | Functional | Must | BO-04 | BR-01, BR-09 | EP-01 | US-01 | TC-US-01-1, TC-US-01-2, TC-US-01-3, TC-US-01-4, TC-US-01-5 | Not started | Backlog | Release 1 (MVP)
FR-04 | Submission confirmation | Functional | Must | BO-04, BO-05 | BR-01, BR-06 | EP-01 | US-01 | TC-US-01-1, TC-US-01-2, TC-US-01-3, TC-US-01-4, TC-US-01-5 | Not started | Backlog | Release 1 (MVP)
FR-05 | Location selection | Functional | Must | BO-04, BO-06 | BR-01, BR-07 | EP-01 | US-02 | TC-US-02-1, TC-US-02-2, TC-US-02-3 | Not started | Backlog | Release 1 (MVP)
FR-06 | Return trip | Functional | Must | BO-01, BO-03, BO-07 | BR-03, BR-12 | EP-01 | US-03 | TC-US-03-1, TC-US-03-2, TC-US-03-3, TC-US-03-4 | Not started | Backlog | Release 1 (MVP)
FR-07 | Short-notice & out-of-hours warning | Functional | Should | BO-05 | BR-06 | EP-01 | US-05 | TC-US-05-1, TC-US-05-2, TC-US-05-3 | Not started | Backlog | Release 2
FR-08 | Anti-abuse protection | Functional | Must | — | BR-10 | EP-01 | US-06 | TC-US-06-1, TC-US-06-2, TC-US-06-3 | Not started | Backlog | Release 1 (MVP) | Privacy Act 2020
FR-09 | Special requirements | Functional | Should | BO-01, BO-03 | BR-03 | EP-01 | US-04 | TC-US-04-1, TC-US-04-2, TC-US-04-3 | Not started | Backlog | Release 2
FR-10 | Availability hint | Functional | Could | BO-04 | BR-01 | EP-01 | US-07 | TC-US-07-1, TC-US-07-2 | Not started | Backlog | Later
FR-11 | Recurring series | Functional | Must | BO-01 | BR-02 | EP-02 | US-08 | TC-US-08-1, TC-US-08-2, TC-US-08-3 | Not started | Backlog | Release 1 (MVP)
FR-12 | Term & holiday calendar | Functional | Must | BO-01 | BR-02 | EP-02 | US-09 | TC-US-09-1, TC-US-09-2, TC-US-09-3 | Not started | Backlog | Release 1 (MVP)
FR-13 | Occurrence exceptions | Functional | Must | BO-01, BO-05 | BR-02, BR-06 | EP-02 | US-10 | TC-US-10-1, TC-US-10-2 | Not started | Backlog | Release 1 (MVP)
FR-14 | Fixed-trip priority | Functional | Must | BO-01, BO-03 | BR-02, BR-03 | EP-02 | US-11 | TC-US-11-1, TC-US-11-2 | Not started | Backlog | Release 1 (MVP)
FR-15 | Bulk import | Functional | Could | BO-01 | BR-02 | EP-02 | US-12 | TC-US-12-1, TC-US-12-2 | Not started | Backlog | Later
FR-16 | Automatic allocation trigger | Functional | Must | BO-01, BO-03 | BR-03 | EP-03 | US-13 | TC-US-13-1, TC-US-13-2, TC-US-13-3 | Not started | Backlog | Release 1 (MVP)
FR-17 | Hard constraints | Functional | Must | BO-01, BO-02, BO-03 | BR-03, BR-05 | EP-03 | US-14, US-20 | TC-US-14-1, TC-US-14-2, TC-US-14-3, TC-US-20-1, TC-US-20-2, TC-US-20-3 | Not started | Backlog | Release 1 (MVP) | HSWA 2015 / land transport
FR-18 | Preference ranking | Functional | Must | BO-01, BO-03 | BR-03 | EP-03 | US-15 | TC-US-15-1, TC-US-15-2, TC-US-15-3 | Not started | Backlog | Release 1 (MVP)
FR-19 | Allocation explanation | Functional | Should | BO-01, BO-02 | BR-04, BR-11 | EP-03 | US-16 | TC-US-16-1, TC-US-16-2 | Not started | Backlog | Release 2
FR-20 | No-fit handling | Functional | Must | BO-01, BO-02, BO-03 | BR-03, BR-04 | EP-03 | US-17 | TC-US-17-1, TC-US-17-2, TC-US-17-3 | Not started | Backlog | Release 1 (MVP)
FR-22 | Multi-van split | Functional | Should | BO-01, BO-03 | BR-03 | EP-03 | US-19 | TC-US-19-1, TC-US-19-2 | Not started | Backlog | Release 2
FR-23 | Confirmed bookings locked | Functional | Must | BO-01, BO-02 | BR-04 | EP-03 | US-13, US-24 | TC-US-13-1, TC-US-13-2, TC-US-13-3, TC-US-24-1, TC-US-24-2, TC-US-24-3 | Not started | Backlog | Release 1 (MVP)
FR-25 | Coordinator dashboard | Functional | Must | BO-01, BO-02 | BR-04 | EP-04 | US-22 | TC-US-22-1, TC-US-22-2, TC-US-22-3 | Not started | Backlog | Release 1 (MVP)
FR-26 | Approve | Functional | Must | BO-01, BO-02, BO-05 | BR-04, BR-06 | EP-04 | US-23 | TC-US-23-1, TC-US-23-2, TC-US-23-3 | Not started | Backlog | Release 1 (MVP)
FR-27 | Change booking | Functional | Must | BO-01, BO-02 | BR-04, BR-05 | EP-04 | US-24 | TC-US-24-1, TC-US-24-2, TC-US-24-3 | Not started | Backlog | Release 1 (MVP) | HSWA 2015 / land transport
FR-28 | Decline | Functional | Must | BO-01, BO-02, BO-05 | BR-04, BR-06 | EP-04 | US-25 | TC-US-25-1, TC-US-25-2 | Not started | Backlog | Release 1 (MVP)
FR-29 | Calendar views | Functional | Must | BO-01, BO-02 | BR-04 | EP-04 | US-26 | TC-US-26-1, TC-US-26-2, TC-US-26-3 | Not started | Backlog | Release 1 (MVP)
FR-30 | Booking on behalf | Functional | Must | BO-01, BO-02, BO-04 | BR-01, BR-04 | EP-04 | US-27 | TC-US-27-1, TC-US-27-2 | Not started | Backlog | Release 1 (MVP)
FR-31 | Drag and drop | Functional | Could | BO-01, BO-02 | BR-04 | EP-04 | US-28 | TC-US-28-1, TC-US-28-2 | Not started | Backlog | Later
FR-32 | Daily run sheet | Functional | Should | BO-01, BO-02 | BR-04 | EP-04 | US-29 | TC-US-29-1, TC-US-29-2 | Not started | Backlog | Release 2
FR-33 | Status notifications | Functional | Must | BO-05 | BR-06 | EP-05 | US-30 | TC-US-30-1, TC-US-30-2, TC-US-30-3, TC-US-30-4 | Not started | Backlog | Release 1 (MVP)
FR-34 | Trip reminder | Functional | Should | BO-05 | BR-06 | EP-05 | US-31 | TC-US-31-1, TC-US-31-2 | Not started | Backlog | Release 2
FR-35 | Secure self-service link | Functional | Must | BO-05 | BR-06, BR-10 | EP-05 | US-32 | TC-US-32-1, TC-US-32-2, TC-US-32-3, TC-US-32-4 | Not started | Backlog | Release 1 (MVP) | Privacy Act 2020
FR-36 | Coordinator alerts | Functional | Should | BO-01, BO-02 | BR-04 | EP-05 | US-33 | TC-US-33-1, TC-US-33-2 | Not started | Backlog | Release 2
FR-38 | Hired van register | Functional | Must | BO-02, BO-06 | BR-07, BR-05 | EP-06 | US-35 | TC-US-35-1, TC-US-35-2, TC-US-35-3, TC-US-35-4 | Not started | Backlog | Release 1 (MVP) | HSWA 2015 / land transport
FR-39 | Locations & travel-time overrides | Functional | Must | BO-06 | BR-07 | EP-06 | US-36 | TC-US-36-1, TC-US-36-2, TC-US-36-3 | Not started | Backlog | Release 1 (MVP)
FR-40 | Unavailability & compliance evidence | Functional | Must | BO-02 | BR-05 | EP-03 | US-37, US-20 | TC-US-37-1, TC-US-37-2, TC-US-20-1, TC-US-20-2, TC-US-20-3 | Not started | Backlog | Release 1 (MVP) | HSWA 2015 / land transport
FR-42 | Settings | Functional | Must | BO-06 | BR-07 | EP-06 | US-39 | TC-US-39-1, TC-US-39-2 | Not started | Backlog | Release 1 (MVP)
FR-43 | User management | Functional | Must | — | BR-10 | EP-08 | US-43 | TC-US-43-1, TC-US-43-2, TC-US-43-3 | Not started | Backlog | Release 1 (MVP) | Privacy Act 2020
FR-44 | Utilisation & efficiency report | Functional | Should | BO-03, BO-07 | BR-08, BR-12 | EP-07 | US-40 | TC-US-40-1, TC-US-40-2 | Not started | Backlog | Release 2
FR-45 | Demand & unmet-demand report | Functional | Should | BO-03 | BR-08 | EP-07 | US-40 | TC-US-40-1, TC-US-40-2 | Not started | Backlog | Release 2
FR-46 | Export | Functional | Should | BO-03 | BR-08 | EP-07 | US-41 | TC-US-41-1 | Not started | Backlog | Release 2
FR-47 | Odometer capture | Functional | Could | BO-03 | BR-08 | EP-07 | US-42 | TC-US-42-1 | Not started | Backlog | Later
FR-48 | Staff authentication | Functional | Must | — | BR-10 | EP-08 | US-43 | TC-US-43-1, TC-US-43-2, TC-US-43-3 | Not started | Backlog | Release 1 (MVP) | Privacy Act 2020
FR-49 | Privacy notice & retention | Functional | Must | — | BR-10 | EP-08 | US-44 | TC-US-44-1, TC-US-44-2 | Not started | Backlog | Release 1 (MVP) | Privacy Act 2020
FR-50 | Audit trail | Functional | Must | BO-02 | BR-11 | EP-08 | US-45 | TC-US-45-1, TC-US-45-2 | Not started | Backlog | Release 1 (MVP)
FR-51 | Role-based access | Functional | Must | — | BR-10 | EP-08 | US-43 | TC-US-43-1, TC-US-43-2, TC-US-43-3 | Not started | Backlog | Release 1 (MVP) | Privacy Act 2020
FR-52 | Address lookup | Functional | Must | BO-03, BO-04, BO-07 | BR-01, BR-12 | EP-09 | US-53 | TC-US-53-1, TC-US-53-2, TC-US-53-3 | Not started | Backlog | Release 1 (MVP)
FR-53 | Travel-time calculation | Functional | Must | BO-03, BO-07 | BR-12 | EP-09 | US-53 | TC-US-53-1, TC-US-53-2, TC-US-53-3 | Not started | Backlog | Release 1 (MVP)
FR-54 | Extra stops on a request | Functional | Should | BO-03, BO-04, BO-07 | BR-01, BR-12 | EP-09 | US-46 | TC-US-46-1, TC-US-46-2, TC-US-46-3 | Not started | Backlog | Release 2
FR-55 | Time flexibility | Functional | Should | BO-03, BO-07 | BR-12 | EP-09 | US-47 | TC-US-47-1, TC-US-47-2, TC-US-47-3 | Not started | Backlog | Release 2
FR-56 | Route insertion & pooling | Functional | Must | BO-01, BO-03, BO-07 | BR-03, BR-12 | EP-09 | US-48 | TC-US-48-1, TC-US-48-2, TC-US-48-3 | Not started | Backlog | Release 1 (MVP)
FR-57 | Optimise day | Functional | Must | BO-01, BO-02, BO-03, BO-07 | BR-04, BR-12 | EP-09 | US-49 | TC-US-49-1, TC-US-49-2, TC-US-49-3 | Not started | Backlog | Release 1 (MVP)
FR-58 | Gap-filling between legs | Functional | Must | BO-03, BO-07 | BR-12 | EP-09 | US-54 | TC-US-54-1, TC-US-54-2, TC-US-54-3 | Not started | Backlog | Release 1 (MVP)
FR-59 | Route map | Functional | Should | BO-01, BO-02, BO-03, BO-07 | BR-04, BR-12 | EP-09 | US-50 | TC-US-50-1, TC-US-50-2 | Not started | Backlog | Release 2
FR-60 | Manual route editing | Functional | Should | BO-01, BO-02 | BR-04 | EP-09 | US-51 | TC-US-51-1, TC-US-51-2 | Not started | Backlog | Release 2
FR-61 | Driver route link | Functional | Must | BO-05 | BR-06, BR-10 | EP-05 | US-52 | TC-US-52-1, TC-US-52-2, TC-US-52-3, TC-US-52-4 | Not started | Backlog | Release 1 (MVP) | Privacy Act 2020
FR-62 | Contracted hours & breaks | Functional | Must | BO-02 | BR-05 | EP-03 | US-55 | TC-US-55-1, TC-US-55-2 | Not started | Backlog | Release 1 (MVP) | HSWA 2015 / land transport
FR-63 | Supplier & driver details | Functional | Must | BO-02, BO-06 | BR-05, BR-07 | EP-06 | US-56 | TC-US-56-1, TC-US-56-2 | Not started | Backlog | Release 1 (MVP) | HSWA 2015 / land transport
FR-64 | Record delays | Functional | Could | BO-05 | BR-06 | EP-09 | US-57 | TC-US-57-1, TC-US-57-2 | Not started | Backlog | Later
NFR-01 | A first-time requester can complete the form without help. | Non-functional | Must | BO-04 | BR-09 | All | — | TC-NFR-01 | Not started | Backlog | Release 1 (MVP)
NFR-02 | Plain language throughout; no technical jargon; one question | Non-functional | Must | BO-04 | BR-09 | All | — | TC-NFR-02 | Not started | Backlog | Release 1 (MVP)
NFR-03 | Conforms to WCAG 2.2 Level AA (contrast, keyboard use, scree | Non-functional | Must | BO-04 | BR-09 | All | — | TC-NFR-03 | Not started | Backlog | Release 1 (MVP)
NFR-04 | Works on phones (360 px wide and up), tablets and desktops; | Non-functional | Must | BO-04 | BR-09 | All | — | TC-NFR-04 | Not started | Backlog | Release 1 (MVP)
NFR-05 | Pages load in 3 seconds or less on 4G; a single request is p | Non-functional | Must | — | BR-07 | All | — | TC-NFR-05 | Not started | Backlog | Release 1 (MVP)
NFR-06 | 99.5% availability 06:30–19:00 Mon–Fri (NZ time); maintenanc | Non-functional | Should | — | BR-07 | All | — | TC-NFR-06 | Not started | Backlog | Release 2
NFR-07 | Supports at least 20 vans, 50 locations, 20 staff users and | Non-functional | Must | — | BR-07 | All | — | TC-NFR-07 | Not started | Backlog | Release 1 (MVP)
NFR-08 | HTTPS (TLS 1.2+), encryption at rest, OWASP Top 10 controls, | Non-functional | Must | — | BR-10 | All | — | TC-NFR-08 | Not started | Backlog | Release 1 (MVP) | Privacy Act 2020
NFR-09 | Complies with NZ Privacy Act 2020 (collection limited to wha | Non-functional | Must | — | BR-10 | All | — | TC-NFR-09 | Not started | Backlog | Release 1 (MVP) | Privacy Act 2020
NFR-10 | Data hosted in New Zealand or Australia unless the college a | Non-functional | Should | — | BR-10 | All | — | TC-NFR-10 | Not started | Backlog | Release 2
NFR-11 | Daily backups; RPO 24 h; RTO 1 school day; restore tested ea | Non-functional | Must | — | BR-07 | All | — | TC-NFR-11 | Not started | Backlog | Release 1 (MVP)
NFR-12 | NZ time zone including daylight saving; dates DD/MM/YYYY; ti | Non-functional | Must | — | BR-07 | All | — | TC-NFR-12 | Not started | Backlog | Release 1 (MVP)
NFR-13 | Vans, drivers, locations, travel times, term dates, template | Non-functional | Must | — | BR-07 | All | — | TC-NFR-13 | Not started | Backlog | Release 1 (MVP)
NFR-14 | Context help on each screen; one-page quick guide for reques | Non-functional | Should | — | BR-07 | All | — | TC-NFR-14 | Not started | Backlog | Release 2
NFR-15 | Audit records cannot be edited or deleted by any user role a | Non-functional | Must | — | BR-10 | All | — | TC-NFR-15 | Not started | Backlog | Release 1 (MVP)
NFR-16 | On a replay of 4 weeks of real requests, the optimised plan | Non-functional | Should | — | BR-12 | All | — | TC-NFR-16 | Not started | Backlog | Release 2
NFR-17 | If the map/routing service is unavailable, booking and appro | Non-functional | Must | — | BR-12 | All | — | TC-NFR-17 | Not started | Backlog | Release 1 (MVP)

## Open Questions
ID | Question | Why it matters | Owner | Affects | Answer | Status
Q-01 | Who drives the vans – dedicated drivers, or the staff member who requests the trip? What licence/endorsement is required? | Decides whether driver allocation (FR-24, US-21) is needed in Release 1. | Project Sponsor / H&S | FR-24, FR-41, BRL-05 | Vans are hired with drivers. | Answered
Q-02 | What exactly are the '3 school destinations' – college campuses, partner schools, or activity venues? Please list all regular locations. | Location list and travel-time table. | Transport Coordinators | FR-05, FR-39 | 3 branches of the school; staff also request transport for other errands. | Answered
Q-03 | Seat capacity (excluding driver) and special features of each van? | Capacity rules and the 'smallest van' preference. | Business Manager | BRL-02, BRL-08 | Seating capacity is set when defining each van. Actual van capacities are still needed as data (D-03). | Answered
Q-04 | Minimum notice period and operating hours? Are weekend trips allowed? | Default settings and urgent flag. | Transport Coordinators | BRL-13 |  | Open
Q-05 | Should fixed-trip occurrences be auto-confirmed, or approved like other requests? | Coordinator workload vs control. | Transport Coordinators | FR-14, FR-26 |  | Open
Q-06 | Is the name + phone public form enough, or should we check college email addresses / send an SMS code? | Abuse risk vs ease of use. | Project Sponsor / Privacy Officer | FR-08 |  | Open
Q-07 | Is SMS budget approved? Expected monthly requests? | Notification channel and cost. | Business Manager | FR-33, FR-34 |  | Open
Q-08 | When requests clash, who has priority beyond 'fixed trips first' (e.g. by department or year level)? | Priority rules. | Project Sponsor | BRL-07 |  | Open
Q-09 | Does the college use a student management / SSO system we should integrate with (staff directory, term dates)? | Integration scope and login method. | IT Support | FR-12, FR-48 |  | Open
Q-10 | How long should request records be kept (default proposed: 24 months)? | Retention setting. | Privacy Officer | FR-49 |  | Open
Q-11 | Do coordinators need to approve from their phones while away from a desk? | Mobile design of coordinator screens. | Transport Coordinators | NFR-04 |  | Open
Q-12 | Do trips need a passenger (student) list for H&S/EOTC purposes? | Significant privacy and scope impact. | H&S / EOTC Coordinator | Scope |  | Open
Q-13 | Hosting preference, budget, and build vs buy (off-the-shelf fleet booking tools exist)? | Solution approach and data residency. | Project Sponsor / IT | NFR-10, R-08 |  | Open
Q-14 | For fixed trips, does the van usually wait at the venue, or drop off and return later? | The biggest efficiency lever: a van that drops off and returns can serve other trips in between. | Sports Coordinator | BRL-06, FR-06 | Sometimes they wait; if another trip can be finished before the return trip, the van does it. | Answered
Q-15 | How is the hire charged (per day, per hour, per km)? What are each van's contracted hours? How much notice is needed for an extra van? | Sets the optimisation goal (BRL-08 weights) and the 'extra van needed' option. | Business Manager | BRL-05, BRL-08, FR-38 |  | Open
Q-16 | How much extra ride time is acceptable when sharing a van, and what default pickup flexibility? | Pooling limits (BRL-11, BRL-17). | Transport Coordinators | BRL-11, BRL-17 |  | Open
Q-17 | Budget for a map/routing service? Any preferred provider? | Integration cost and design. | IT Support / Business Manager | FR-52, FR-53, D-07 |  | Open
Q-18 | Do errands sometimes carry goods only (no passengers)? Do goods take up seats? | Capacity model for goods. | Transport Coordinators | BRL-02 |  | Open
Q-19 | Where does each van start and end its day – a branch, or the supplier's depot? | First/last leg of every route. | Hire supplier | FR-38 |  | Open

## Risks
ID | Risk | Likelihood | Impact | Mitigation | Owner | Status
R-01 | Staff keep booking informally (low adoption) | Medium | High | QR-code posters, one-minute form, coordinators redirect informal requests to the form, and leadership endorsement |  | Open
R-02 | Spam or fake submissions on the public form | Medium | Medium | CAPTCHA/honeypot, rate limits, first-time-phone review (BRL-15); every request needs coordinator approval anyway |  | Open
R-03 | Inaccurate travel times cause late trips | Medium | Medium | Review travel times after month 1 using coordinator feedback; buffers configurable |  | Open
R-04 | Coordinators don't trust automatic allocation | Low | High | Plain-English explanations (FR-19); coordinators approve everything; tune rules in pilot |  | Open
R-05 | SMS costs higher than expected | Low | Low | Monitor volume; combine fixed-trip confirmations; email fallback |  | Open
R-06 | Privacy breach of requester data | Low | High | Minimal data, 2FA, encryption, retention/anonymisation, privacy impact assessment |  | Open
R-07 | Vehicle compliance dates not kept up to date | Medium | High | Reminders (FR-40); named data owner (D-03); monthly check |  | Open
R-08 | Custom build costs more than an off-the-shelf product | Medium | Medium | Run a build-vs-buy evaluation against this specification before committing |  | Open
R-09 | Route optimisation is complex, and a custom build may overrun | Medium | High | Use a proven solver or routing API rather than hand-built logic; run a 1–2 sprint technical spike first; replay real data (NFR-16) |  | Open
R-10 | A gap job overruns and the return group is kept waiting | Medium | Medium | Safety buffer (BRL-06), 'Van must stay' option, gap jobs only when travel times are reliable, delay recording (US-57) |  | Open
R-11 | Shared rides make trips too long, or staff dislike sharing | Medium | Medium | Maximum extra ride time (BRL-11), requester flexibility choice, clear 'Shared van' messaging; review complaints in the pilot |  | Open
R-12 | Map service costs or offshore data processing | Low | Medium | Cache travel times; send addresses only (no names/phones) to the map service; cover this in the privacy notice (IPP 12) |  | Open